Deliverables Checklist Replacement of Nurse Call Systems and/or Staff Paging Systems in a Hospital Aligned to RIBA Plan of Work 2020 & relevant SHTMs

This checklist covers replacement or major upgrade of:

- Nurse call systems (patient-to-nurse, staff emergency, speech, presence, logging)

- Associated or standalone staff paging / radio paging / staff attack systems

- Integration with bedhead services, cardiac arrest alerts, and other clinical communication systems

Primary References

| System | Key Guidance |
| --- | --- |
| Nurse Call Systems | SHTM 08-03 – Specialist services: Bedhead services |
| Supporting | SHTM 00 (Policies & principles) SHTM 08-01 (Acoustics – for sound levels) SHTM 06 series (Electrical) Clinical risk assessment & Medical Gas / Fire interfaces where relevant |
| Paging / Staff Alert Systems | Manufacturer standards + clinical risk assessment + radio licensing / EMC requirements Often integrated with SHTM 08-03 systems |

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Business case / need identification (system age, reliability, clinical risk, logging capability) |  | SHTM 00, SHTM 08-03 |
| Strategic brief & outcomes (patient safety, staff response times, resilience, audit trail) |  | SHTM 00 |
| High-level clinical / operational impact assessment |  | Clinical risk |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Project Brief (nurse call scope, paging scope, integration requirements) |  | SHTM 08-03 |
| Existing system condition survey & call logging analysis |  | SHTM 08-03 |
| Clinical needs assessment (specialties, dependency levels, speech vs non-speech) |  | SHTM 08-03 |
| Initial risk register (service continuity, infection control, false calls) |  | SHTM 00, CDM |
| Project Execution Plan & procurement strategy |  | — |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Concept options (wired vs wireless, speech capability, paging integration, centralised logging) |  | SHTM 08-03 |
| Outline system architecture and zoning strategy |  | SHTM 08-03 |
| Preliminary device schedule (bedhead, WC, staff emergency, indicators, pagers) |  | SHTM 08-03 |
| Outline specifications & preliminary cost plan |  | — |
| Design risk assessment |  | CDM, SHTM 08-03 |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Coordinated design (device locations, cable routes / wireless coverage, staff bases, indicators) |  | SHTM 08-03 |
| Spatial coordination with bedhead services, electrical, data and fire systems |  | SHTM 00 |
| Updated cost plan, risk register & phasing / temporary cover strategy |  | — |

Stage 4 – Technical Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full technical design drawings, schematics and device schedules |  | SHTM 08-03 |
| Detailed specifications (call points, handsets, indicators, controllers, speech units, paging interfaces, logging software) |  | SHTM 08-03 |
| Power supply, resilience and backup arrangements |  | SHTM 06 series |
| Integration design (cardiac arrest, fire alert, staff attack, BMS if required) |  | SHTM 08-03 |
| Wireless coverage / radio survey (if applicable) |  | Manufacturer + licensing |
| Building Warrant / Building (Scotland) Regulations 2004 compliance information (Schedule 3 where the works affect an existing occupied building) |  | — |
| Pre-construction information & Construction Phase Plan input |  | CDM |
| Designer’s Risk Assessment & residual risks |  | CDM, SHTM 08-03 |
| Tender documentation / Scope of Works |  | — |
| Clinical stakeholder review and approval |  | SHTM 08-03 |

Stage 5 – Manufacturing and Construction

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Contractor method statements, phasing & temporary nurse call / paging cover |  | — |
| Material & equipment certificates |  | Manufacturer |
| Installation of devices, cabling / wireless infrastructure, controllers and indicators |  | SHTM 08-03 |
| Integration testing with other systems |  | — |
| Progress records, quality inspections, change control log |  | — |
| Temporary system cover arrangements |  | Critical for patient safety |
| Decommissioning records of redundant equipment |  | — |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full commissioning, functional testing and validation records |  | SHTM 08-03 |
| Call logging, reporting and audit trail verification |  | SHTM 08-03 |
| As-fitted drawings, device schedules and configuration records |  | SHTM 08-03 |
| Comprehensive O&M manuals and user guides |  | SHTM 08-03 |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for nursing and estates staff |  | SHTM 08-03 |
| Residual risk register |  | CDM |
| Practical Completion / handover certificate |  | — |
| Clinical acceptance / sign-off |  | Essential |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Soft landings / post-occupancy review (response times, usability, false call rates) |  | SHTM 00 |
| Updated operational procedures and call response protocols |  | — |
| Ongoing maintenance, testing and call logging review regime |  | SHTM 08-03 |
| Defects liability records & final account |  | — |
| Lessons learned report |  | SHTM 00 |

Cross-Stage / Continuous Deliverables

- Live Health & Safety File

- Project risk register

- Change control log

- Clinical stakeholder engagement at key gateways

- Maintenance of continuous nurse call / staff alert cover during works

- Evidence of compliance with manufacturer requirements and clinical risk assessments

- Evidence of current PVG Scheme membership for all contractor personnel attending site

- Where works are in, adjacent to, above or below a room housing ionising-radiation imaging equipment (CT, X-ray, fluoroscopy, nuclear medicine): confirm Radiation Protection Adviser (RPA) sign-off on shielding integrity per the Room/Ward/Theatre Refresh checklist - a separate gate from HAI-SCRIBE, not covered by it