Deliverables Checklist Replacement / Upgrade of Automatic Doors in a Hospital Aligned to RIBA Plan of Work 2020 & relevant Standards

This checklist follows the exact same format as the other Hard FM system checklists. It is intended for projects involving the replacement, major upgrade or installation of automatic (power-operated) doors in hospital premises (sliding, swing, revolving and folding doorsets, including fire/smoke-resisting doorsets, access-controlled doors and doors on isolation-room or theatre lobbies).

Primary Guidance References

| System Element | Key Guidance |
| --- | --- |
| Linen Decontamination | HTM 01-04 Decontamination of linen for health and social care - thermal disinfection cycle minimum 71C for at least 3 minutes, or 65C for at least 10 minutes |
| Pressure Equipment | Pressure Systems Safety Regulations 2000 - steam-heated ironers/calendars and steam-fed washer-extractors require a Written Scheme of Examination by a Competent Person |
| Fire Risk | Lint/fluff accumulation in tumble dryers and extract ductwork is a well-documented industrial fire source - BESA/insurer guidance on dryer duct and lint-trap cleaning regimes |
| Chemical Handling | COSHH (laundry detergents, disinfectants); F-Gas Regulations where refrigerant dryers are used |
| Supporting | PUWER 1998 (washer-extractor, ironer, calendar guarding/interlocks); infection control 'dirty-to-clean' flow separation, cross-referenced to IPC |
| Core Standards | HTM 01-04, Pressure Systems Safety Regulations 2000, COSHH, PUWER 1998 |

Key Principles

- Thermal disinfection cycles for health and social care linen must meet HTM 01-04 — 71°C for at least 3 minutes, or 65°C for at least 10 minutes — verified, not assumed, for each washer-extractor programme.

- Steam-heated ironers, calendars and presses are pressure systems under the Pressure Systems Safety Regulations 2000 — a Written Scheme of Examination applies, the same statutory regime as this project's Steam Systems and Compressed Air checklists.

- Lint and dust accumulation in tumble dryers and ducting is a well-documented industrial-laundry fire risk — ongoing extract/lint-trap cleaning is a distinct maintenance deliverable, not covered by general PPM.

- Laundry chemicals (detergents, sours, disinfectants) fall under COSHH — dosing system design and safe handling/storage are design-stage deliverables, not just an operational afterthought.

- Continuity of linen supply, or a contingency/outsourced-laundry arrangement, must be maintained during any phased replacement.

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Business case / need identification (plant age, reliability, capacity, thermal-disinfection compliance) |  | PM check |
| Strategic brief & project outcomes (linen-supply continuity, infection control) |  |  |
| High-level infection control impact assessment |  | HTM 01-04 |
| Confirmation of steam-heated versus electric equipment (pressure systems scope trigger) |  | Pressure Systems Safety Regulations 2000 |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Project Brief (washer-extractor/dryer/ironer schedule, thermal-disinfection capacity) |  |  |
| Existing condition surveys, including current Written Scheme of Examination status for pressure equipment |  | Pressure Systems Safety Regulations 2000 |
| Initial risk register (linen-supply continuity, fire risk, thermal-disinfection failure = infection risk) |  | CDM |
| Engagement with IPC, Linen Services, Estates and Fire Safety Advisor |  | Essential |
| Project Execution Plan & procurement strategy |  |  |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Concept design options (washer-extractor barrier-wash technology, dirty-to-clean one-way flow separation) |  | HTM 01-04 |
| Outline thermal-disinfection validation strategy |  | HTM 01-04 |
| Design risk assessment (pressure systems, CDM) |  |  |
| Preliminary specifications & cost plan |  |  |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Coordinated design (barrier/flow separation layout, steam/pressure pipework routing, dryer duct routing) |  | HTM 01-04 |
| Spatial coordination with structure and adjacent clean/dirty zones |  |  |
| Updated cost plan and risk register |  |  |
| Temporary linen-supply continuity strategy during works |  | Critical for clinical service |

Stage 4 – Technical Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full technical design - thermal-disinfection cycle validation design |  | HTM 01-04 |
| Pressure system design and Written Scheme of Examination provisions |  | Pressure Systems Safety Regulations 2000 |
| Dryer duct and lint-trap fire-safety design |  |  |
| Electrical and steam services design |  |  |
| IPC design confirmation of dirty-to-clean flow separation |  | HAI-SCRIBE |
| Building Regulations / statutory compliance information |  | Building (Scotland) Regulations 2004 |
| Pre-construction information & input to Construction Phase Plan |  | CDM |
| Designer's Risk Assessment & residual risks |  | CDM |
| Tender documentation / Scope of Works / pricing schedules |  |  |
| Stakeholder review and approval of design (Estates, Linen Services, IPC, Fire Safety Advisor) |  | Essential |
| Obtain minimum of two competitive quotations |  | Critical commercial requirement |
| Submit quotations, cost comparison and recommendation to PFI Board / NHS for lifecycle approval |  |  |
| PRE-CONTRACT HOLD POINT: No contractor appointment and no further progression until written cost approval is received |  | Clear commercial & governance cut-off |

Stage 5 – Manufacturing and Construction

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Contractor method statements, phasing & temporary linen-supply continuity arrangements |  | Critical for clinical service |
| Material & equipment certificates, including pressure vessel certificates |  | Pressure Systems Safety Regulations 2000 |
| Installation of washer-extractors, dryers, ironers/calendars and controls |  |  |
| Written Scheme of Examination established prior to first use of pressure equipment |  | Pressure Systems Safety Regulations 2000 |
| Progress records, quality inspections, change control log |  |  |
| IPC sign-off for the dirty-to-clean flow arrangement |  | HAI-SCRIBE |
| Decommissioning & disposal records of redundant plant |  |  |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full commissioning & thermal-disinfection validation testing records (temperature/time proof) |  | HTM 01-04 |
| Pressure system Written Scheme of Examination in place and first periodic examination completed |  | Pressure Systems Safety Regulations 2000 |
| Dirty-to-clean flow verification |  | HAI-SCRIBE |
| As-fitted drawings and control system configuration records |  |  |
| Comprehensive O&M manuals |  |  |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for Linen Services staff |  |  |
| Practical Completion / handover certificate |  |  |
| Confirmation of ongoing periodic thermal-disinfection re-validation regime |  | HTM 01-04 |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Soft landings / post-occupancy review (reliability, linen-supply continuity, user feedback) |  |  |
| Ongoing thermal-disinfection validation regime in operation (periodic re-test) |  | HTM 01-04 |
| Ongoing periodic examination regime for pressure equipment under the Written Scheme |  | Pressure Systems Safety Regulations 2000 |
| Ongoing lint-trap and dryer-duct fire-safety cleaning regime |  |  |
| Defects liability records & final account |  |  |
| Lessons learned report |  |  |

Cross-Stage / Continuous Deliverables

Live Health & Safety File

Project risk register (updated at each stage)

Change control log

Stakeholder engagement (Estates, Linen Services, IPC, Fire Safety Advisor) at key gateways

Maintenance of linen-supply continuity throughout the works

Evidence of compliance with HTM 01-04 and the Pressure Systems Safety Regulations 2000

Ongoing periodic thermal-disinfection validation and pressure-system examination regime

- Evidence of current PVG Scheme membership for all contractor personnel attending site

- Where works are in, adjacent to, above or below a room housing ionising-radiation imaging equipment (CT, X-ray, fluoroscopy, nuclear medicine): confirm Radiation Protection Adviser (RPA) sign-off on shielding integrity per the Room/Ward/Theatre Refresh checklist - a separate gate from HAI-SCRIBE, not covered by it