Deliverables Checklist Replacement / Upgrade of Automatic Doors in a Hospital Aligned to RIBA Plan of Work 2020 & relevant Standards

This checklist follows the exact same format as the other Hard FM system checklists. It is intended for projects involving the replacement, major upgrade or installation of automatic (power-operated) doors in hospital premises (sliding, swing, revolving and folding doorsets, including fire/smoke-resisting doorsets, access-controlled doors and doors on isolation-room or theatre lobbies).

Primary Guidance References

| System Element | Key Guidance |
| --- | --- |
| Healthcare Waste Segregation & Classification | SHTN 03-01 NHSScotland Waste Management Guidance - the primary Scottish colour-coded segregation standard; HTM 07-01 Safe and sustainable management of healthcare waste (2023) is the parallel NHS England document |
| Legal Framework | Special Waste (Amendment) (Scotland) Regulations 2004 (healthcare/clinical waste classed as special waste); Environmental Protection Act 1990 Duty of Care; SEPA Waste Carrier Licensing |
| Equipment Safety | PUWER 1998 (macerators, compactors); COSHH (hazardous/cytotoxic waste handling) |
| Supporting | Fire risk in waste storage areas - a recurring hospital fire-safety finding; not a substitute for the foul-drainage pipework covered in Drainage & Foul Water System Replacement / Above-ground Drainage & Public Health Systems Replacement |
| Core Standards | SHTN 03-01, HTM 07-01, Special Waste (Amendment) (Scotland) Regulations 2004, SEPA licensing, PUWER 1998, COSHH |

Key Principles

- NHS Scotland's colour-coded waste segregation regime is set out in SHTN 03-01 (NHSScotland Waste Management Guidance) — Scotland's own primary source, distinct from NHS England's HTM 07-01.

- Special/clinical waste handling and carriage is governed by the Special Waste (Amendment) (Scotland) Regulations 2004 and the Duty of Care under the Environmental Protection Act 1990 — the waste carrier must hold a current SEPA licence.

- Macerators and compactors are subject to PUWER 1998 — guarding, isolation and safe operating procedures are design and commissioning deliverables, not assumed from the manufacturer's standard package.

- Handling of clinical/hazardous waste streams falls under COSHH — segregation-point design and PPE/handling procedures for staff are a distinct deliverable from the equipment installation itself.

- Continuity of waste removal, or an equivalent temporary arrangement, must be maintained throughout any phased replacement — waste storage capacity cannot be allowed to back up into clinical areas.

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Business case / need identification (waste-store/macerator/compactor condition, capacity, segregation compliance) |  | SHTN 03-01 |
| Strategic brief & project outcomes (regulatory compliance driver, sustainability/circular-economy alignment) |  | HTM 07-01 (2023) |
| High-level operational impact assessment (waste-collection continuity across the site during works) |  |  |
| Confirmation of waste streams affected (clinical, offensive, domestic, recyclable segregation categories) |  | SHTN 03-01 |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Project Brief (scope of segregation stores, macerators, compactors, chutes) |  |  |
| Existing condition surveys and current SEPA waste carrier licence status |  | SEPA |
| Initial risk register (waste-accumulation risk, biohazard exposure, fire risk in waste stores) |  | CDM |
| Engagement with Estates, IPC, Sustainability/Environmental lead |  | Essential |
| Project Execution Plan & procurement strategy |  |  |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Concept design options (segregation-store layout and colour-coding, macerator versus compactor technology) |  | SHTN 03-01 |
| Outline temporary waste-handling continuity strategy |  | Critical for clinical service |
| Design risk assessment (fire risk, COSHH, CDM) |  |  |
| Preliminary specifications & cost plan |  |  |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Coordinated design (waste-store locations/access routes, chute routing, compactor/macerator plant room) |  |  |
| Spatial coordination with fire compartmentation and vehicle access for collection |  |  |
| Updated cost plan and risk register |  |  |
| Temporary waste-handling continuity arrangements finalised |  |  |

Stage 4 – Technical Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full technical design - segregation-store specification and colour-coding per SHTN 03-01 |  | SHTN 03-01 |
| Macerator/compactor specification and biohazard containment design |  | PUWER 1998 |
| Fire risk design for waste storage areas (fire loading, compartmentation, sprinkler/detection interface) |  |  |
| Building Regulations / statutory compliance information |  | Building (Scotland) Regulations 2004 |
| Pre-construction information & input to Construction Phase Plan |  | CDM |
| Designer's Risk Assessment & residual risks |  | CDM |
| Tender documentation / Scope of Works / pricing schedules |  |  |
| Stakeholder review and approval of design (Estates, IPC, Sustainability lead, Fire Safety Advisor) |  | Essential |
| Obtain minimum of two competitive quotations |  | Critical commercial requirement |
| Submit quotations, cost comparison and recommendation to PFI Board / NHS for lifecycle approval |  |  |
| PRE-CONTRACT HOLD POINT: No contractor appointment and no further progression until written cost approval is received |  | Clear commercial & governance cut-off |

Stage 5 – Manufacturing and Construction

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Contractor method statements, phasing & temporary waste-handling continuity arrangements |  | Critical for clinical service |
| Material & equipment certificates |  |  |
| Installation of segregation stores, macerators, compactors and chutes |  |  |
| Commissioning of macerator/compactor safety interlocks |  | PUWER 1998 |
| Progress records, quality inspections, change control log |  |  |
| IPC sign-off for any works in clinical-waste-adjacent areas |  | HAI-SCRIBE |
| Decommissioning & disposal records of redundant equipment |  |  |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full commissioning records - macerator/compactor safety interlock testing |  | PUWER 1998 |
| Segregation-store signage and colour-coding verification against SHTN 03-01 |  | SHTN 03-01 |
| Updated SEPA waste carrier licence and consignment-note arrangements confirmed |  | SEPA |
| As-fitted drawings and control system configuration records |  |  |
| Comprehensive O&M manuals |  |  |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for Estates and ward/clinical staff (segregation training coordinated with IPC) |  |  |
| Practical Completion / handover certificate |  |  |
| Confirmation of ongoing periodic segregation-compliance audit regime |  | SHTN 03-01 |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Soft landings / post-occupancy review (reliability, waste-collection continuity, user feedback) |  |  |
| Ongoing waste-segregation audit regime in operation |  | SHTN 03-01 |
| Ongoing macerator/compactor PUWER inspection and maintenance regime |  | PUWER 1998 |
| SEPA waste carrier licence renewal tracking |  | SEPA |
| Defects liability records & final account |  |  |
| Lessons learned report |  |  |

Cross-Stage / Continuous Deliverables

Live Health & Safety File

Project risk register (updated at each stage)

Change control log

Stakeholder engagement (Estates, IPC, Sustainability/Environmental lead, Fire Safety Advisor) at key gateways

Maintenance of waste-collection continuity throughout the works

Evidence of compliance with SHTN 03-01 segregation standard and the Special Waste (Amendment) (Scotland) Regulations 2004

Ongoing periodic segregation-compliance audit regime

- Evidence of current PVG Scheme membership for all contractor personnel attending site

- Where works are in, adjacent to, above or below a room housing ionising-radiation imaging equipment (CT, X-ray, fluoroscopy, nuclear medicine): confirm Radiation Protection Adviser (RPA) sign-off on shielding integrity per the Room/Ward/Theatre Refresh checklist - a separate gate from HAI-SCRIBE, not covered by it