Systems Updated with Clear Cut-Off Language

| No. | System | Status |
| --- | --- | --- |
| 9 | Electrical Services | Updated |
| 10 | Domestic Hot & Cold Water | Updated |
| 11 | Chilled Water / Cooling | Updated |
| 12 | Steam Systems | Updated |
| 13 | Fire Suppression Systems | Updated |
| 15 | Pneumatic Tube Systems | Updated |
| 18 | Ward / Theatre Refurbishment | Updated |

All other systems already aligned cleanly and now carry the same explicit Stage 4 approval gate wording for consistency.

Therse are the amendments to the systems mentioned above that need updated in the templates. .

Standardised Stage Wording (to be used in all 18 checklists)

Stage 2 – Concept Design

- High-level design risk assessment only

- Outline construction / phasing principles (no method statements)

Stage 3 – Spatial Coordination

- High-level temporary arrangements strategy only

- Updated cost plan

- Preparation for competitive quoting

Stage 4 – Technical Design (Critical Gate)

- Full technical design and specifications

- Tender documentation / Scope of Works

- Obtain minimum two competitive quotes

- Submit quotes + cost comparison to PFI Board / NHS for lifecycle approval

- No construction or detailed contractor documentation until written approval is received

Stage 5 – Manufacturing and Construction

- Contractor’s detailed Method Statements

- Full RAMS

- Detailed temporary works designs

- Only after formal cost approval and contractor appointment