Deliverables Checklist Replacement / Upgrade of Building Management System (BMS) / Building Energy Management System (BEMS) in a Hospital Aligned to RIBA Plan of Work 2020 & relevant SHTMs

This checklist follows the same format as the previous checklists (nurse call, fire alarm, lifts, medical gases, heating/ventilation, etc.). It is intended for projects involving the full replacement or major upgrade of a Building Management System (BMS) / Building Energy Management System (BEMS).

Note: Minor BMS modifications (adding points for new plant) are already covered within the system-specific checklists previously created. This checklist is for a standalone or major BMS project.

Primary References

| Aspect | Key Guidance |
| --- | --- |
| Overarching | SHTM 00 – Policies and principles of best practice guidance |
| Electrical / Controls | SHTM 06 series (Electrical services) |
| Linked Systems | SHTM 03-01 (Ventilation – critical environment monitoring & control) SHTM 04-01 (Water systems – temperature, flow and plant monitoring) SHTM 08-02 (Lifts – interfaces if applicable) SHTM 82 (Fire – plant shutdown / interface) |
| Industry Standards | CIBSE Guides (especially Guide H – Building Control Systems) BSRIA guidance (BG 1/2020, BG 9/2011 etc.) BS EN ISO 16484 series (Building automation and control systems) Manufacturer standards & cybersecurity guidance |

Key principles

- BMS is a critical system for monitoring and controlling heating, ventilation, critical environments, energy, plant status and alarms.

- Continuity of monitoring and control of critical plant must be maintained during the works.

- Cybersecurity, resilience, alarm management and future expandability are essential.

- Integration with existing and new plant (boilers, AHUs, medical gases, fire, lifts, etc.) must be carefully managed.

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Business case / need identification (system age, reliability, energy performance, cybersecurity, expandability) |  | SHTM 00 |
| Strategic brief & project outcomes (resilience, energy management, critical alarms, future-proofing) |  | SHTM 00 |
| High-level clinical / operational impact assessment |  | SHTM 00 |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Project Brief (scope of BMS replacement, integration requirements, energy monitoring needs) |  | SHTM 00 |
| Existing BMS condition survey, point schedule audit and residual life assessment |  | — |
| Stakeholder requirements capture (estates, clinical, energy, infection control, IT/cyber) |  | SHTM 00 |
| Initial risk register (loss of monitoring/control, critical plant, cybersecurity) |  | SHTM 00, CDM |
| Project Execution Plan & procurement strategy |  | — |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Concept design options (centralised vs distributed, open protocol, cloud/hybrid, energy analytics) |  | SHTM 00, CIBSE Guide H |
| Outline system architecture, network topology and resilience strategy |  | — |
| High-level point schedule and integration matrix with other systems |  | Linked SHTMs |
| Outline specifications & preliminary cost plan |  | — |
| Design risk assessment (including cybersecurity) |  | CDM, SHTM 00 |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Coordinated design (controller locations, network routes, server/head-end rooms, HMI locations) |  | SHTM 00 |
| Spatial coordination with electrical, data, plantrooms and other services |  | SHTM 06 series |
| Updated cost plan, risk register & high-level phasing / temporary monitoring strategy |  | — |

Stage 4 – Technical Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full technical design drawings, network schematics and system architecture |  | CIBSE / BSRIA |
| Detailed point schedules, control strategies and cause-and-effect matrices |  | Linked SHTMs (03-01, 04-01 etc.) |
| Detailed specifications (controllers, sensors, actuators, servers, software, graphics, cybersecurity) |  | Manufacturer + industry standards |
| Integration design with existing/new plant (boilers, AHUs, medical gases, fire, lifts, nurse call etc.) |  | Relevant system SHTMs |
| Energy monitoring, reporting and analytics specification |  | — |
| Cybersecurity design and resilience measures |  | Current NHS / national guidance |
| Electrical design associated with BMS power and controls |  | SHTM 06 series |
| Building Regulations / statutory compliance information |  | — |
| Pre-construction information & input to Construction Phase Plan |  | CDM |
| Designer’s Risk Assessment & residual risks |  | CDM, SHTM 00 |
| Tender documentation / Scope of Works / pricing schedules |  | — |
| Stakeholder review and approval of design (including clinical & energy teams) |  | SHTM 00 |

Stage 5 – Manufacturing and Construction

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Contractor method statements, detailed phasing & temporary monitoring/control arrangements |  | Critical for plant safety |
| Material & equipment certificates (controllers, sensors, software licences) |  | — |
| Installation of field devices, controllers, network infrastructure and head-end equipment |  | — |
| Software configuration, graphics development and control strategy implementation |  | — |
| Integration testing with other building systems |  | Linked SHTMs |
| Progress records, quality inspections, change control log |  | — |
| Temporary BMS / monitoring cover arrangements |  | Essential |
| Decommissioning records of redundant BMS equipment |  | — |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full commissioning, functional testing and validation records |  | CIBSE / BSRIA guidance |
| Point-to-point testing, control strategy proving and alarm testing |  | — |
| Graphics, user interface and reporting verification |  | — |
| Cybersecurity testing and hardening confirmation |  | — |
| As-fitted drawings, final point schedules, network diagrams and configuration backups |  | — |
| Comprehensive O&M manuals, user guides and training materials |  | SHTM 00 |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for estates, energy and clinical users |  | SHTM 00 |
| Residual risk register |  | CDM |
| Practical Completion / handover certificate |  | — |
| Formal client / stakeholder acceptance |  | Essential |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Soft landings / post-occupancy evaluation (performance, usability, energy savings, alarm management) |  | SHTM 00 |
| Updated operational procedures, alarm response protocols and energy reporting routines |  | — |
| Ongoing maintenance, software update and cybersecurity regime |  | — |
| Defects liability records & final account |  | — |
| Lessons learned report |  | SHTM 00 |

Cross-Stage / Continuous Deliverables

- Live Health & Safety File

- Project risk register (updated at each stage)

- Change control log

- Stakeholder engagement (estates, energy, clinical, IT/cyber, infection control) at key gateways

- Maintenance of continuous monitoring and control of critical plant throughout the works

- Evidence of compliance with manufacturer requirements, cybersecurity standards and relevant SHTMs

- Configuration backups and disaster recovery arrangements

- Evidence of current PVG Scheme membership for all contractor personnel attending site