Deliverables Checklist Replacement / Upgrade of Above-ground Drainage / Public Health Systems in a Hospital Aligned to RIBA Plan of Work 2020 & relevant Standards

This checklist follows the exact same format as the Electrical Services, Domestic Hot & Cold Water, Chilled Water, Steam, Fire Suppression, Security, Pneumatic Tube, Medical Gas, Lifts and BMS checklists. It is intended for projects involving the replacement, major upgrade or significant modification of Above-ground Drainage and Public Health Systems in hospital premises (foul/soil & waste systems, stacks, vents, floor drains, channels, interceptors, and associated access points).

Primary Guidance References

| System Element | Key Guidance |
| --- | --- |
| Above-ground Drainage / Public Health Systems | Building Standards (Scotland) – Section 3 Environment BS EN 12056 – Gravity drainage systems inside buildings SHTM 00 – Policies and principles |
| Supporting | Infection Prevention & Control (IPC) requirements SHTM 04-01 principles (where water systems interface) CDM 2015 |
| Core Considerations | Maintainability, accessibility for rodding/cleaning, infection control, odour control, capacity, and future flexibility |

Key Principles

- Above-ground drainage systems must protect health by safely removing foul and waste water while preventing odours, blockages and cross-contamination.

- Accessibility for maintenance, cleaning and future modification is essential in a hospital environment.

- Infection control and cleanability of accessible components are important considerations.

- Continuity of drainage service to clinical and support areas must be maintained during the works.

- Design should minimise future disruption for maintenance.

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Business case / need identification (system age, blockages, odours, capacity, maintainability, compliance) |  | SHTM 00 |
| Strategic brief & project outcomes (reliability, maintainability, infection control, odour control, future flexibility) |  | SHTM 00 |
| High-level clinical / operational impact assessment |  | SHTM 00, IPC |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Project Brief (scope of foul, waste, vent and associated drainage works) |  | SHTM 00 |
| Existing system condition surveys (stacks, branches, floor drains, access points, known problem areas) |  | — |
| Review of historical blockage, flooding or odour issues |  | — |
| Initial risk register (loss of service, flooding, infection, odour, access for maintenance) |  | SHTM 00, CDM, IPC |
| Project Execution Plan & procurement strategy |  | — |
| Engagement with Estates, IPC, clinical and housekeeping stakeholders |  | Important |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Concept design options (stack strategy, materials, access provision, future flexibility) |  | BS EN 12056 |
| Outline drainage strategy (foul, waste, venting, gradients, capacity) |  | Building Standards (Scotland) |
| Preliminary schematic layouts and stack schedules |  | — |
| Outline specifications & preliminary cost plan |  | — |
| Design risk assessment (including maintenance access and IPC) |  | CDM, IPC |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Coordinated design (stack locations, branch routes, floor drains, access points, plant interfaces) |  | BS EN 12056 |
| Spatial coordination with structure, other services, ceilings and clinical layouts |  | SHTM 00 |
| Updated cost plan, risk register & high-level phasing / temporary drainage strategy |  | — |
| Confirmation of access and maintenance strategy |  | Critical for long-term performance |

Stage 4 – Technical Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full technical design drawings, schematics, stack schedules and drain schedules |  | BS EN 12056, Building Standards |
| Detailed specifications (pipework materials, fittings, floor drains, channels, traps, access fittings, insulation if required) |  | BS EN 12056 |
| Venting strategy and anti-siphonage measures |  | BS EN 12056 |
| Access, rodding and cleaning point design |  | Maintainability focus |
| Interface design with below-ground drainage and sanitary fittings |  | — |
| Building Standards (Scotland) compliance information |  | Section 3 Environment |
| Pre-construction information & input to Construction Phase Plan |  | CDM |
| Designer’s Risk Assessment & residual risks |  | CDM, IPC |
| Tender documentation / Scope of Works / pricing schedules |  | — |
| Stakeholder review and approval of design (Estates, IPC) |  | Recommended |

Stage 5 – Manufacturing and Construction

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Contractor method statements, detailed phasing & temporary drainage arrangements |  | Important for operational areas |
| Material & equipment certificates (pipework, fittings, drains, traps) |  | Manufacturer / BS EN |
| Installation of above-ground drainage pipework, stacks, branches, floor drains and access fittings |  | BS EN 12056 |
| Gradient, support and jointing quality records |  | — |
| Air / water testing records |  | BS EN 12056 |
| Progress records, quality inspections, change control log |  | — |
| Temporary drainage / hybrid working arrangements (if phased) |  | Where required |
| Decommissioning & strip-out records of redundant drainage systems |  | — |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full testing and commissioning records (air tests, water tests, performance verification) |  | BS EN 12056 |
| As-fitted drawings, schematics, stack schedules and access point registers |  | Essential for future maintenance |
| Comprehensive O&M manuals, including cleaning and maintenance procedures |  | SHTM 00 |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for estates and facilities staff |  | — |
| Residual risk register |  | CDM |
| Practical Completion / handover certificate |  | — |
| Formal client / Estates acceptance |  | — |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Soft landings / post-occupancy review (blockages, odours, maintainability, user feedback) |  | SHTM 00 |
| Updated maintenance and cleaning regime |  | — |
| Ongoing inspection and performance monitoring |  | — |
| Defects liability records & final account |  | — |
| Lessons learned report |  | SHTM 00 |

Cross-Stage / Continuous Deliverables

- Live Health & Safety File

- Project risk register (updated at each stage)

- Change control log

- Estates and Infection Prevention & Control engagement at key gateways

- Maintenance of adequate drainage service to operational areas throughout the works

- Evidence of compliance with Building Standards (Scotland), BS EN 12056 and manufacturer requirements

- Full as-fitted information to support future maintenance and modifications