Deliverables Checklist Replacement / Upgrade of Electrical Services in a Hospital Aligned to RIBA Plan of Work 2020 & relevant SHTMs

This checklist follows the exact same format as the Medical Gas, Lifts, Fire Alarm, Nurse Call and BMS checklists. It is intended for projects involving the replacement, major upgrade or significant modification of Electrical Services in hospital premises (LV distribution, switchgear, UPS, IPS, standby generators, lighting, small power, and associated controls).

Primary SHTM / Guidance References

| System Element | Key Guidance |
| --- | --- |
| Electrical Services | SHTM 06 series (particularly SHTM 06-01 Electrical services supply and distribution, SHTM 06-02, SHTM 06-03) |
| Overarching | SHTM 00 – Policies and principles |
| Linked Systems | SHTM 03-01 (Ventilation – critical power), SHTM 04-01 (Water – pump power), SHTM 08-02 (Lifts), SHTM 02-01 (Medical gases – alarm power), Firecode (emergency lighting & power) |
| Core Standards | BS 7671 (IET Wiring Regulations), BS EN 61439, BS 5266 (Emergency lighting), BS 8519 (management of fire-related power systems), Electricity at Work Regulations, CDM 2015 |

Key Principles

- Resilience of supply to critical clinical areas is paramount.

- Continuity of electrical supply must be maintained during the works (phased working or temporary supplies).

- Discrimination, selectivity, UPS/IPS provision and emergency generation are critical design considerations.

- Emergency lighting and life-safety systems must remain operational throughout.

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Business case / need identification (system age, resilience, capacity, compliance, energy performance) |  | SHTM 00, SHTM 06 |
| Strategic brief & project outcomes (clinical resilience, continuity of supply, future capacity) |  | SHTM 00 |
| High-level clinical / operational impact assessment |  | SHTM 00 |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Project Brief (scope of electrical works, resilience requirements, critical areas) |  | SHTM 00, SHTM 06 |
| Existing system condition surveys (LV/HV distribution, switchgear, UPS, IPS, generators, lighting, earthing) |  | SHTM 06 series |
| Load assessment and residual capacity analysis |  | SHTM 06 |
| Initial risk register (loss of supply, critical areas, temporary power, discrimination) |  | SHTM 00, CDM |
| Project Execution Plan & procurement strategy |  | — |
| Engagement with clinical, estates and IT stakeholders |  | SHTM 00 |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Concept design options (resilience levels, UPS/IPS strategy, generator provision, distribution philosophy) |  | SHTM 06 |
| Outline electrical strategy (primary/secondary supplies, essential vs non-essential) |  | SHTM 06 series |
| Preliminary single-line diagrams and load schedules |  | SHTM 06 |
| Outline specifications & preliminary cost plan |  | — |
| Design risk assessment |  | CDM, SHTM 00, SHTM 06 |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Coordinated design (switch rooms, distribution routes, generator location, UPS rooms, containment) |  | SHTM 06 |
| Spatial coordination with structure, mechanical services, fire compartments and other systems |  | SHTM 00 |
| Updated cost plan, risk register & high-level phasing / temporary supply strategy |  | — |
| Confirmation of emergency power provisions for critical areas |  | SHTM 06 |

Stage 4 – Technical Design

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Full technical design drawings, single-line diagrams, schematics and containment layouts |  | SHTM 06 series |
| Detailed specifications (switchgear, distribution boards, UPS, IPS, generators, cabling, lighting, controls) |  | SHTM 06, BS 7671 |
| Discrimination / selectivity studies and protection coordination |  | SHTM 06, BS 7671 |
| UPS / IPS autonomy and configuration design |  | SHTM 06 |
| Standby generator sizing, fuel storage and control philosophy |  | SHTM 06 |
| Emergency lighting design (BS 5266) |  | BS 5266, Firecode |
| Earthing, bonding and lightning protection design |  | BS 7671, SHTM 06 |
| Building Regulations / statutory compliance information |  | — |
| Pre-construction information & input to Construction Phase Plan |  | CDM |
| Designer’s Risk Assessment & residual risks |  | CDM, SHTM 06 |
| Tender documentation / Scope of Works / pricing schedules |  | — |
| Stakeholder review and approval of design |  | SHTM 06 |

Stage 5 – Manufacturing and Construction

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Contractor method statements, detailed phasing & temporary power arrangements |  | Critical for continuity |
| Material & equipment certificates (switchgear, UPS, generators, cable, luminaires) |  | BS 7671 / manufacturer |
| Installation of distribution equipment, containment, cabling, UPS, generators and lighting |  | SHTM 06, BS 7671 |
| Earthing and bonding installation records |  | BS 7671 |
| Progress records, quality inspections, change control log |  | — |
| Temporary supply / hybrid working arrangements (if phased) |  | Essential |
| Decommissioning & strip-out records of redundant electrical equipment |  | — |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Full testing & commissioning records (insulation resistance, continuity, earth loop, RCD, functional, load bank tests) |  | SHTM 06, BS 7671 |
| Discrimination / protection proving records |  | SHTM 06 |
| UPS / IPS autonomy and changeover tests |  | SHTM 06 |
| Generator load and changeover tests |  | SHTM 06 |
| Emergency lighting duration and functional tests |  | BS 5266 |
| As-fitted drawings, single-line diagrams, schedules and certification (Electrical Installation Certificate, etc.) |  | BS 7671, SHTM 06 |
| Comprehensive O&M manuals and log books |  | SHTM 06 |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for estates staff |  | SHTM 06 |
| Residual risk register |  | CDM |
| Practical Completion / handover certificate |  | — |
| Formal client / Responsible Person acceptance |  | SHTM 06 |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Soft landings / post-occupancy review (performance, resilience, energy, user feedback) |  | SHTM 00 |
| Updated maintenance regime, inspection schedules and emergency procedures |  | SHTM 06 |
| Ongoing statutory inspection and testing records |  | Electricity at Work Regulations |
| Defects liability records & final account |  | — |
| Lessons learned report |  | SHTM 00 |

Cross-Stage / Continuous Deliverables

- Live Health & Safety File

- Project risk register (updated at each stage)

- Change control log

- Stakeholder engagement (estates, clinical, IT, fire safety) at key gateways

- Maintenance of continuous electrical supply to critical clinical areas throughout the works

- Evidence of compliance with BS 7671, SHTM 06 series and manufacturer requirements

- Permit-to-Work and isolation procedures