Deliverables Checklist Replacement / Upgrade of Fire Suppression Systems in a Hospital Aligned to RIBA Plan of Work 2020 & relevant SHTMs / Standards

It is intended for projects involving the replacement, major upgrade or significant modification of Fire Suppression Systems in hospital premises (sprinklers, water mist, gaseous suppression, foam systems, and associated controls and interfaces).

Primary SHTM / Guidance References

| System Element | Key Guidance |
| --- | --- |
| Fire Suppression Systems | NHSScotland Firecode – particularly SHTM 81 (Fire safety in the design of healthcare premises) and associated supplements SHTM 82 (Fire detection and alarm systems – interfaces) |
| Overarching | SHTM 00 – Policies and principles SHTM 86 (Fire risk assessment) |
| Core Standards | BS EN 12845 (Automatic sprinkler systems) BS EN 15004 / ISO 14520 (Gaseous fire extinguishing systems) Relevant standards for water mist, foam, etc. CDM 2015 Building Standards (Scotland) – Fire |

Key Principles

- Fire suppression systems form a critical part of the overall fire safety strategy.

- Continuity of protection must be maintained during the works (phased isolation or temporary measures).

- Full interface with the fire detection and alarm system (SHTM 82) is essential.

- Fire Safety Advisor / Authorising Engineer involvement and approval is required at key stages.

- System design must align with the building’s fire strategy and compartmentation.

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Business case / need identification (system age, reliability, coverage, compliance with current fire strategy) |  | SHTM 00, SHTM 81 |
| Strategic brief & project outcomes (life safety, property protection, business continuity, compliance) |  | SHTM 00 |
| High-level clinical / operational impact assessment |  | SHTM 00, SHTM 86 |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Project Brief (scope of suppression works – sprinkler / water mist / gas / foam, areas covered) |  | SHTM 00, SHTM 81 |
| Existing system condition surveys (pipework, valves, pump sets, cylinders, nozzles, interfaces) |  | SHTM 81 |
| Review of current fire strategy and fire risk assessment |  | SHTM 81, SHTM 86 |
| Initial risk register (loss of protection, false discharge, water damage, clinical impact) |  | SHTM 00, CDM, SHTM 86 |
| Project Execution Plan & procurement strategy |  | — |
| Formal engagement with Fire Safety Advisor / Authorising Engineer |  | SHTM 81, SHTM 86 |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Concept design options (sprinkler vs water mist vs gaseous, coverage extent, resilience) |  | SHTM 81, BS EN 12845 / relevant standards |
| Outline suppression strategy aligned with fire strategy and compartmentation |  | SHTM 81 |
| Preliminary schematic layouts and hazard classification |  | Relevant BS EN standards |
| Outline specifications & preliminary cost plan |  | — |
| Design risk assessment |  | CDM, SHTM 00, SHTM 81 |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Coordinated design (pipe routes, valve sets, pump rooms, cylinder locations, nozzle positions) |  | SHTM 81 |
| Spatial coordination with structure, ceilings, other services and fire compartments |  | SHTM 81 |
| Updated cost plan, risk register & high-level phasing / temporary protection strategy |  | — |
| Confirmation of interface requirements with fire alarm system |  | SHTM 82 |

Stage 4 – Technical Design

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Full technical design drawings, schematics and layouts |  | SHTM 81, BS EN 12845 / relevant standards |
| Detailed specifications (pipework, valves, pumps, cylinders, nozzles, controls, detection interfaces) |  | Relevant BS EN / ISO standards |
| Hydraulic calculations (sprinkler / water mist) or agent quantity calculations (gaseous) |  | BS EN 12845 or BS EN 15004 |
| Cause & effect / interface matrix with fire detection & alarm system |  | SHTM 82 |
| Water supply / storage or agent storage design |  | Relevant standards |
| Building Regulations / Fire Standards compliance information |  | Building Standards (Scotland) |
| Pre-construction information & input to Construction Phase Plan |  | CDM |
| Designer’s Risk Assessment & residual risks |  | CDM, SHTM 81 |
| Tender documentation / Scope of Works / pricing schedules |  | — |
| Fire Safety Advisor / Authorising Engineer review and approval of design |  | SHTM 81, SHTM 86 |

Stage 5 – Manufacturing and Construction

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Contractor method statements, detailed phasing & temporary protection arrangements |  | Critical for life safety |
| Material & equipment certificates (pipework, valves, pumps, cylinders, nozzles) |  | Relevant standards |
| Installation of pipework, valve sets, pumps, cylinders, nozzles and controls |  | Relevant BS EN standards |
| Pressure testing, flushing and integrity testing records |  | BS EN 12845 / relevant standards |
| Interface installation and preliminary testing with fire alarm system |  | SHTM 82 |
| Progress records, quality inspections, change control log |  | — |
| Temporary protection / hybrid working arrangements (if phased) |  | Essential |
| Decommissioning & strip-out records of redundant suppression equipment |  | — |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Full commissioning, testing and certification records |  | Relevant BS EN / ISO standards |
| Hydraulic / agent discharge performance verification (where safe and appropriate) |  | — |
| Interface and cause-and-effect testing with fire detection & alarm system |  | SHTM 82 |
| As-fitted drawings, schematics, valve schedules and calculation packages |  | SHTM 81 |
| Comprehensive O&M manuals and log books |  | SHTM 00 |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for estates and fire response teams |  | SHTM 81, SHTM 83 |
| Residual risk register |  | CDM |
| Practical Completion / handover certificate |  | — |
| Formal acceptance by Fire Safety Advisor / Authorising Engineer |  | SHTM 81, SHTM 86 |
| Updated fire risk assessment reflecting the new system |  | SHTM 86 |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Soft landings / post-occupancy review (system performance, false discharge risk, user feedback) |  | SHTM 00 |
| Updated maintenance, inspection and testing regime |  | Relevant BS EN standards, SHTM 81 |
| Ongoing interface testing with fire alarm system |  | SHTM 82 |
| Defects liability records & final account |  | — |
| Lessons learned report |  | SHTM 00 |

Cross-Stage / Continuous Deliverables

- Live Health & Safety File

- Project risk register (updated at each stage)

- Change control log

- Fire Safety Advisor / Authorising Engineer engagement at key gateways

- Maintenance of adequate fire suppression protection throughout the works

- Evidence of compliance with SHTM 81, relevant BS EN / ISO standards and the building fire strategy

- Full certification and calculation packages