Deliverables Checklist Replacement / Upgrade of Automatic Doors in a Hospital Aligned to RIBA Plan of Work 2020 & relevant Standards

This checklist follows the exact same format as the other Hard FM system checklists. It is intended for projects involving the replacement, major upgrade or installation of automatic (power-operated) doors in hospital premises (sliding, swing, revolving and folding doorsets, including fire/smoke-resisting doorsets, access-controlled doors and doors on isolation-room or theatre lobbies).

Primary Guidance References

| System Element | Key Guidance |
| --- | --- |
| Automatic Doors | BS EN 16005 (power-operated pedestrian doorsets - safety in use) SHTM 00 - Policies and principles |
| Fire/Smoke-Resisting Doorsets | BS EN 16034 (fire resisting and/or smoke control doorsets) Fire (Scotland) Act 2005 Part 3, Fire Safety (Scotland) Regulations 2006 |
| Supporting | Equality Act 2010 (accessible access) SHTM 03-01 / HAI-SCRIBE (where a door forms part of a pressure-cascade boundary) CDM 2015 |
| Core Standards | BS EN 16005, BS EN 16034, Fire (Scotland) Act 2005, Building (Scotland) Regulations 2004 (means of escape) |

Key Principles

- Automatic doors on a fire compartment line or escape route must fail safe to a manually openable state on power loss or fire-alarm activation.

- Where a door forms part of an isolation-room or theatre-lobby pressure cascade, it is part of infection-control containment, not just access control - replacement or upgrade needs an IPC-aware design check (HAI-SCRIBE), not a purely mechanical one.

- Accessible-access requirements (Equality Act 2010) must be confirmed for any door serving a public or patient route.

- Continuity of the affected route, or an equivalent temporary arrangement, must be maintained during the works.

- Fire/smoke-rated doorset sign-off (Fire Safety Advisor, BS EN 16034) and safety-in-use sign-off (BS EN 16005) are separate assessments - both are required, neither substitutes for the other.

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Business case / need identification (door condition, reliability, safety-in-use compliance, access control requirements) |  | SHTM 00 |
| Strategic brief & project outcomes (accessibility, infection control containment, fire compartmentation) |  | SHTM 00 |
| High-level clinical / operational impact assessment (affected routes, IPC-sensitive locations) |  | SHTM 00, HAI-SCRIBE |
| Confirmation of which doors are fire/smoke-rated versus standard access doors |  | BS EN 16034 |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Project Brief (scope of doors, locations, fire/smoke rating requirements, accessibility needs) |  | SHTM 00 |
| Existing door condition surveys (operators, sensors, seals, fire/smoke rating evidence, safety-in-use compliance) |  | BS EN 16005, BS EN 16034 |
| Location risk assessment - identify any doors on isolation-room or theatre-lobby pressure-cascade boundaries |  | HAI-SCRIBE |
| Initial risk register (loss of access control, fire compartmentation breach, IPC containment breach, accessibility) |  | SHTM 00, CDM |
| Project Execution Plan & procurement strategy |  |  |
| Engagement with Estates, Fire Safety Advisor, IPC (where relevant) and Access/Equality lead |  | Essential |
| Confirmation of any Radiation Protection Adviser (RPA) interest where a door adjoins an imaging suite |  | IRR17 |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Concept design options (door type - sliding, swing, revolving, folding; operator technology; fire/smoke rating) |  | BS EN 16005 |
| Outline fail-safe strategy (power loss, fire-alarm interface, manual override) |  | BS EN 16034 |
| Preliminary location plan and route-continuity strategy |  |  |
| Outline specifications & preliminary cost plan |  |  |
| Design risk assessment (including IPC / pressure-cascade risk where relevant) |  | CDM, HAI-SCRIBE |
| Confirmation of accessible-access requirements for the specific route |  | Equality Act 2010 |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Coordinated design (door locations, structural openings, frame/header details, sensor zones) |  |  |
| Spatial coordination with fire compartmentation, structure and adjacent clinical spaces |  | SHTM 00, BS EN 16034 |
| Updated cost plan, risk register & high-level phasing / temporary access strategy |  |  |
| Confirmation of pressure-cascade continuity strategy for any IPC-relevant doors during the works |  | HAI-SCRIBE |
| Confirmation of RPA / shielding position for any imaging-adjacent doors |  | IRR17 |

Stage 4 – Technical Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full technical design drawings, door schedules and fixing details |  | BS EN 16005, BS EN 16034 |
| Detailed specifications (operators, sensors, safety edges, seals, fire/smoke rating, finishes) |  | BS EN 16005, BS EN 16034 |
| Fail-safe / power-loss / fire-alarm interface design |  | BS EN 16034, SHTM 82 |
| Electrical and access-control system design (card readers, interlocks, BMS integration) |  | SHTM 06 series |
| IPC / pressure-cascade design confirmation for relevant doors |  | HAI-SCRIBE |
| Building Regulations / statutory compliance information (means of escape, accessibility) |  | Building (Scotland) Regs 2004, Equality Act 2010 |
| Pre-construction information & input to Construction Phase Plan |  | CDM |
| Designer’s Risk Assessment & residual risks |  | CDM |
| Tender documentation / Scope of Works / pricing schedules |  |  |
| Stakeholder review and approval of design (Estates, Fire Safety Advisor, IPC where relevant) |  | Essential |
| Obtain minimum of two competitive quotations |  | Critical commercial requirement |
| Submit quotations, cost comparison and recommendation to PFI Board / NHS for lifecycle approval |  |  |
| PRE-CONTRACT HOLD POINT: No contractor appointment and no further progression until written cost approval is received |  | Clear commercial & governance cut-off |

Stage 5 – Manufacturing and Construction

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Contractor method statements, detailed phasing & temporary access/route arrangements |  | Critical for clinical service |
| Material & equipment certificates (operators, sensors, fire/smoke-rated doorsets) |  | BS EN 16034 |
| Installation of doors, frames, operators, sensors and controls |  |  |
| Fail-safe and fire-alarm interface testing during installation |  | BS EN 16034 |
| Progress records, quality inspections, change control log |  |  |
| Temporary access / route arrangements (if phased) |  | Essential |
| IPC sign-off for any works on pressure-cascade-relevant doors |  | HAI-SCRIBE |
| Decommissioning & disposal records of redundant doors |  |  |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full commissioning & safety-in-use testing records (force/energy limits, sensor zones, fail-safe operation) |  | BS EN 16005 |
| Fire/smoke-rating commissioning and fire-alarm interface verification |  | BS EN 16034, SHTM 82 |
| Accessible-access verification for the completed route |  | Equality Act 2010 |
| As-fitted drawings, door schedules and control system configuration records |  |  |
| Comprehensive O&M manuals |  | SHTM 00 |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for estates staff |  | SHTM 00 |
| Residual risk register |  | CDM |
| Practical Completion / handover certificate |  |  |
| Formal client / stakeholder acceptance |  |  |
| Confirmation of ongoing periodic safety-in-use inspection regime |  | BS EN 16005 |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Soft landings / post-occupancy review (reliability, user feedback, accessibility) |  | SHTM 00 |
| Periodic safety-in-use inspection regime in operation |  | BS EN 16005 |
| Ongoing fire/smoke-rated doorset inspection regime, aligned to the fire risk assessment cycle |  | BS EN 16034 |
| Defects liability records & final account |  |  |
| Lessons learned report |  | SHTM 00 |

Cross-Stage / Continuous Deliverables

- Live Health & Safety File

- Project risk register (updated at each stage)

- Change control log

- Stakeholder engagement (Estates, Fire Safety Advisor, IPC, Access/Equality lead) at key gateways

- Maintenance of continuity for the affected access route(s) throughout the works

- Evidence of compliance with BS EN 16005, BS EN 16034 and manufacturer requirements

- Ongoing periodic safety-in-use and fire/smoke-rated doorset inspection regime

- Evidence of current PVG Scheme membership for all contractor personnel attending site

- Where works are in, adjacent to, above or below a room housing ionising-radiation imaging equipment (CT, X-ray, fluoroscopy, nuclear medicine): confirm Radiation Protection Adviser (RPA) sign-off on shielding integrity per the Room/Ward/Theatre Refresh checklist - a separate gate from HAI-SCRIBE, not covered by it