Deliverables Checklist
Replacement / Upgrade of Domestic Hot & Cold Water Systems in a Hospital
Aligned to RIBA Plan of Work 2020 & relevant SHTMs

Primary SHTM / Guidance References

| System Element | Key Guidance |
| --- | --- |
| Domestic Hot & Cold Water Systems | SHTM 04-01 – Water safety (Parts A, B, C, D, E, F & G) |
| Overarching | SHTM 00 – Policies and principles |
| Linked Systems | SHTM 03-01 (Ventilation – if linked), SHTM 06 series (Electrical power to pumps/controls), SHTM 08-03 (Bedhead services – TMVs), BMS interfaces |
| Core Standards | HSE ACOP L8 & HSG 274, BS EN 806, BS 8558, Scottish Water Byelaws, CDM 2015 |

Key Principles

- Control of Legionella and other waterborne pathogens is paramount.

- Water Safety Group (WSG) engagement and approval is required at key stages.

- Continuity of hot and cold water supply to clinical areas must be maintained during the works.

- Temperature control, stagnation prevention, material selection and monitoring are critical.

- Full compliance with SHTM 04-01 is expected for both design and operational management.

Key Governance Rule
A clear Pre-Contract Hold Point exists inside Stage 4.
No contractor appointment and no Stage 5 works may proceed until:

- Minimum two competitive quotes have been obtained (with contingency), and

- Formal lifecycle/cost approval has been received from the PFI Board or NHS, and

- Written approval of the SBAR has been received from the Water Safety Group.

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Business case / need identification (system age, Legionella risk, temperature performance, resilience, water quality) |  | SHTM 00, SHTM 04-01 |
| Strategic brief & project outcomes (patient safety, Legionella control, continuity of supply, energy efficiency) |  | SHTM 00 |
| High-level clinical / operational impact assessment |  | SHTM 00, SHTM 04-01 |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Project Brief (scope of hot & cold water works, temperature regime, TMV strategy, monitoring requirements) |  | SHTM 00, SHTM 04-01 |
| Existing system condition surveys (storage, distribution, pumps, calorifiers, TMVs, dead legs, water quality baseline) |  | SHTM 04-01 Part A & B |
| Water risk assessment review and gap analysis |  | SHTM 04-01, HSE L8 |
| Initial risk register (Legionella, loss of supply, temperature control, materials) |  | SHTM 00, CDM, SHTM 04-01 |
| Project Execution Plan & procurement strategy |  | — |
| Early awareness engagement with Water Safety Group (WSG) |  | SHTM 04-01 Part B |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Concept design options (storage vs instantaneous, central vs local, return systems, TMV strategy, monitoring) |  | SHTM 04-01 Part A |
| Outline water system strategy (temperatures, flow rates, resilience, stagnation prevention) |  | SHTM 04-01 Part A |
| Preliminary schematics and load/demand assessment |  | SHTM 04-01 |
| Outline specifications & preliminary cost plan |  | — |
| Design risk assessment (including Legionella) |  | CDM, SHTM 00, SHTM 04-01 |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Coordinated design (plant locations, pipe routes, storage vessels, pump rooms, access for maintenance) |  | SHTM 04-01 Part A |
| Spatial coordination with structure, electrical, ventilation and other services |  | SHTM 00 |
| Updated cost plan, risk register & high-level phasing / temporary supply strategy (principles only) |  | — |
| Confirmation of temperature monitoring and sampling point strategy |  | SHTM 04-01 |

Stage 4 – Technical Design

(Contains the Pre-Contract Hold Point)

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Developed design / performance specifications (sufficient for accurate pricing) |  | Not full construction-issue drawings |
| Detailed Scope of Works |  | Clear boundaries |
| Updated cost plan including appropriate contingency |  | Realistic budget envelope |
| Water treatment / chemical dosing / temperature control strategy |  | SHTM 04-01 Part A |
| Legionella control measures and schematic risk assessment update |  | SHTM 04-01, HSE L8 |
| Temperature monitoring, sampling points and BMS integration design |  | SHTM 04-01 |
| Electrical design associated with pumps and controls |  | SHTM 06 series |
| Building Warrant / Building (Scotland) Regulations 2004 / Scottish Water Byelaws compliance information (Schedule 3 where the works affect an existing occupied building) |  | Scottish Water Byelaws |
| Designer’s Risk Assessment & residual risks |  | CDM, SHTM 04-01 |
| Pre-construction information & input to Construction Phase Plan |  | CDM |
| Tender documentation / Scope of Works / pricing schedules |  | — |
| Obtain minimum of two competitive quotations |  | Critical commercial requirement |
| Prepare and submit formal SBAR to the Water Safety Group (covering proposed works, water treatment strategy, risk assessment and temporary arrangements) |  | SHTM 04-01 Part B |
| Obtain written WSG approval / endorsement |  | SHTM 04-01 |
| Submit quotations, cost comparison, contingency and recommendation to PFI Board / NHS for lifecycle approval |  | — |
| PRE-CONTRACT HOLD POINT: No contractor appointment and no further progression until written PFI/NHS cost approval and WSG approval are both received |  | Clear commercial & governance cut-off |
| After approval and contractor appointment: complete full technical drawings, final coordination and any remaining design details |  | Post-appointment activity still recorded under Stage 4 |
| RPZ valve installation and annual testing regime (backflow prevention) |  | WRAS AIM 08-01 |
| Dialysis/renal water treatment requirements confirmed (if the system feeds a renal/haemodialysis unit) |  | ISO 23500 |
| Water dispenser/cooler Legionella and biofilm risk confirmed (reservoir-type vs mains-fed/point-of-use) |  | HSG274 / HSE ACOP L8 |

Stage 5 – Manufacturing and Construction

(Only after Stage 4 Hold Point is cleared and contractor is onboarded)

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Contractor’s detailed Method Statements, full RAMS and detailed temporary water supply arrangements |  | Only after appointment |
| Material & equipment certificates (pipework, fittings, vessels, TMVs – WRAS approved where required) |  | SHTM 04-01, Water Byelaws |
| Installation of pipework, storage, pumps, TMVs, insulation and controls |  | SHTM 04-01 Part A |
| Jointing, flushing, cleaning and disinfection records |  | SHTM 04-01 Part D |
| Water sampling and microbiological testing records (pre- and post-disinfection) |  | SHTM 04-01 Parts C & D |
| Progress records, quality inspections, change control log |  | — |
| Temporary supply / hybrid working arrangements (if phased) |  | Essential |
| Decommissioning & strip-out records of redundant water systems |  | SHTM 04-01 |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Full commissioning & validation records (temperatures, flow rates, pressures, TMV performance, pump duties) |  | SHTM 04-01 Part A |
| Final disinfection and microbiological clearance certificates |  | SHTM 04-01 Part D |
| Temperature profiling and balancing records |  | SHTM 04-01 |
| As-fitted drawings, schematics, valve schedules and sampling point registers |  | SHTM 04-01 Part A |
| Comprehensive O&M manuals, including Written Scheme of Control |  | SHTM 04-01 Part B & G |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for estates and clinical staff |  | SHTM 04-01 Part B |
| Residual risk register |  | CDM |
| Practical Completion / handover certificate |  | — |
| Formal Water Safety Group acceptance and updated Water Safety Plan |  | SHTM 04-01 |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Soft landings / post-occupancy review (temperature performance, water quality, user feedback) |  | SHTM 00 |
| Updated Water Safety Plan / Written Scheme of Control |  | SHTM 04-01 Parts B & G |
| Ongoing monitoring, sampling and maintenance regime |  | SHTM 04-01 Part B |
| Defects liability records & final account |  | — |
| Lessons learned report |  | SHTM 00 |

Cross-Stage / Continuous Deliverables

- Live Health & Safety File

- Project risk register (updated at each stage)

- Change control log

- Water Safety Group (WSG) engagement and formal approvals at key gateways

- Maintenance of continuous hot and cold water supply to clinical areas throughout the works

- Evidence of compliance with SHTM 04-01, HSE ACOP L8 / HSG 274 and Water Byelaws

- Full traceability of materials and water quality records

- Evidence of current PVG Scheme membership for all contractor personnel attending site

- Where works are in, adjacent to, above or below a room housing ionising-radiation imaging equipment (CT, X-ray, fluoroscopy, nuclear medicine): confirm Radiation Protection Adviser (RPA) sign-off on shielding integrity per the Room/Ward/Theatre Refresh checklist - a separate gate from HAI-SCRIBE, not covered by it