Deliverables Checklist Replacement / Upgrade of Pneumatic Tube Systems in a Hospital Aligned to RIBA Plan of Work 2020 & relevant Standards

This checklist follows the exact same format as the Electrical Services, Domestic Hot & Cold Water, Chilled Water, Steam, Fire Suppression, Security, Medical Gas, Lifts and BMS checklists. It is intended for projects involving the replacement, major upgrade or significant modification of Pneumatic Tube Systems (PTS) in hospital premises (tube network, stations, blowers/compressors, carriers, control systems, and associated software).

Primary Guidance References

| System Element | Key Guidance |
| --- | --- |
| Pneumatic Tube Systems | Manufacturer standards and technical guidelines SHTM 00 – Policies and principles |
| Supporting | Clinical risk assessment & Infection Prevention & Control (IPC) requirements SHTM 06 series (Electrical power) Noise guidance (SHTM 08-01 Acoustics where relevant) CDM 2015 |
| Core Considerations | Clinical workflow (laboratories, pharmacy, blood bank, theatres, wards) Carrier tracking, priority routing, contamination control and system resilience |

Key Principles

- Pneumatic tube systems are clinically critical for timely transport of specimens, blood products, medicines and documents.

- Continuity of service to key departments (lab, pharmacy, blood bank, critical care, theatres) must be maintained during the works.

- Infection prevention, leak-tightness, cleanability and carrier hygiene are essential.

- System design must support prioritisation, tracking, audit trails and future expandability.

- Strong clinical stakeholder engagement is required throughout.

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Business case / need identification (system age, reliability, capacity, downtime impact, clinical risk) |  | SHTM 00 |
| Strategic brief & project outcomes (clinical turnaround times, resilience, expandable network, infection control) |  | SHTM 00 |
| High-level clinical / operational impact assessment |  | Clinical risk |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Project Brief (scope of network, stations, capacity, priority routing, integration needs) |  | SHTM 00 |
| Existing system condition surveys (tubes, stations, blowers, carriers, control system, leakage, performance) |  | Manufacturer |
| Clinical workflow and demand analysis (lab, pharmacy, blood bank, theatres, wards) |  | Clinical stakeholders |
| Initial risk register (loss of service, specimen integrity, infection, noise, access) |  | SHTM 00, CDM, IPC |
| Project Execution Plan & procurement strategy |  | — |
| Engagement with Pathology, Pharmacy, Blood Bank, Theatres, Critical Care, IPC and Estates |  | Essential |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Concept design options (network topology, station types, blower strategy, carrier technology, software) |  | Manufacturer |
| Outline system strategy (routing, prioritisation, redundancy, future expansion) |  | Clinical requirements |
| Preliminary station location plan and tube routing strategy |  | — |
| Outline specifications & preliminary cost plan |  | — |
| Design risk assessment (including clinical and IPC risks) |  | CDM, IPC |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Coordinated design (tube routes, station locations, blower plant, access for maintenance) |  | — |
| Spatial coordination with structure, ceilings, other services, fire compartments and clinical layouts |  | SHTM 00 |
| Updated cost plan, risk register & high-level phasing / temporary transport strategy |  | — |
| Confirmation of critical department resilience requirements |  | Clinical stakeholders |

Stage 4 – Technical Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full technical design drawings, network schematics and station schedules |  | Manufacturer standards |
| Detailed specifications (tubing, stations, diverters, blowers/compressors, carriers, control system, software) |  | Manufacturer |
| Carrier tracking, prioritisation, alarm and audit trail design |  | Clinical requirements |
| Power, control and network design |  | SHTM 06 series |
| Infection control and cleanability features |  | IPC guidance |
| Noise and vibration considerations |  | SHTM 08-01 where relevant |
| Building Regulations / statutory compliance information |  | — |
| Pre-construction information & input to Construction Phase Plan |  | CDM |
| Designer’s Risk Assessment & residual risks |  | CDM, IPC |
| Tender documentation / Scope of Works / pricing schedules |  | — |
| Clinical and IPC stakeholder review and approval of design |  | Essential |

Stage 5 – Manufacturing and Construction

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Contractor method statements, detailed phasing & temporary specimen/medicine transport arrangements |  | Critical for clinical service |
| Material & equipment certificates (tubing, stations, blowers, carriers, software) |  | Manufacturer |
| Installation of tube network, stations, diverters, blower plant and controls |  | Manufacturer standards |
| Pressure / leakage testing and integrity records |  | Manufacturer |
| Progress records, quality inspections, change control log |  | — |
| Temporary transport / hybrid working arrangements (if phased) |  | Essential |
| Decommissioning & strip-out records of redundant pneumatic tube equipment |  | — |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full commissioning, functional testing and performance verification records |  | Manufacturer |
| Carrier transit time, prioritisation, tracking and empty carrier management tests |  | Clinical requirements |
| Leakage, pressure and system integrity verification |  | — |
| As-fitted drawings, network schematics, station schedules and configuration records |  | — |
| Comprehensive O&M manuals, user guides and administrator documentation |  | SHTM 00 |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for clinical users, porters and estates staff |  | Essential |
| Residual risk register |  | CDM |
| Practical Completion / handover certificate |  | — |
| Formal clinical and client acceptance |  | Essential |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Soft landings / post-occupancy review (transit times, reliability, usability, clinical feedback) |  | SHTM 00 |
| Updated operational procedures, prioritisation rules and contingency plans |  | Clinical stakeholders |
| Ongoing maintenance, carrier hygiene and performance monitoring regime |  | Manufacturer + IPC |
| Defects liability records & final account |  | — |
| Lessons learned report |  | SHTM 00 |

Cross-Stage / Continuous Deliverables

- Live Health & Safety File

- Project risk register (updated at each stage)

- Change control log

- Strong clinical stakeholder engagement (Pathology, Pharmacy, Blood Bank, Theatres, Critical Care, IPC) at key gateways

- Maintenance of continuous pneumatic tube service (or robust temporary alternative) to critical departments throughout the works

- Evidence of compliance with manufacturer requirements, clinical risk assessments and infection control standards

- Full system configuration backups and documentation

- Evidence of current PVG Scheme membership for all contractor personnel attending site