Deliverables Checklist Replacement / Upgrade of Compressed Air Systems (Non-Medical) in a Hospital Aligned to RIBA Plan of Work 2020 & relevant Standards

This checklist follows the exact same format as all previous Hard FM system checklists. It is intended for projects involving the replacement, major upgrade or significant modification of Non-Medical Compressed Air Systems in hospital premises (compressors, receivers, distribution pipework, filters, dryers, pressure regulation, and associated controls).

Note: This checklist covers non-medical compressed air only. Medical compressed air falls under Medical Gas Pipeline Systems (SHTM 02-01) and is covered in the earlier Medical Gas checklist.

Primary Guidance References

| System Element | Key Guidance |
| --- | --- |
| Non-Medical Compressed Air Systems | Pressure Systems Safety Regulations (PSSR) 2000 HSE guidance on PSSR and compressed air SHTM 00 – Policies and principles |
| Supporting | CIBSE Guides Manufacturer standards BS EN standards for compressors, pressure vessels and pipework SHTM 06 series (Electrical power) CDM 2015 |
| Core Considerations | Air quality (as required by the application), pressure stability, moisture control, oil content (if applicable), safety and energy efficiency |

Key Principles

- Non-medical compressed air systems are pressure systems and may fall under the Pressure Systems Safety Regulations (PSSR).

- A Written Scheme of Examination may be required depending on pressure and volume.

- Continuity of supply to critical users (workshops, pneumatic controls, specialist departments) should be maintained where operationally necessary.

- Air quality, dryness and cleanliness must meet the requirements of the end-use applications.

- Safety (pressure relief, guarding, noise, oil carry-over) and energy efficiency are important design considerations.

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Business case / need identification (system age, reliability, capacity, air quality, energy performance, safety) |  | SHTM 00, PSSR |
| Strategic brief & project outcomes (reliability, air quality, safety, energy efficiency, compliance) |  | SHTM 00 |
| High-level operational impact assessment |  | SHTM 00 |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Project Brief (scope of generation, treatment, distribution and user modifications) |  | SHTM 00 |
| Existing system condition surveys (compressors, receivers, dryers, filters, pipework, pressure, air quality) |  | — |
| Review of existing Written Scheme of Examination (if applicable) and inspection history |  | PSSR |
| Initial risk register (pressure system failure, loss of supply, air quality, noise, oil carry-over) |  | SHTM 00, CDM, PSSR |
| Project Execution Plan & procurement strategy |  | — |
| Engagement with Estates, users (workshops, laboratories, etc.) and Competent Person (if required) |  | PSSR |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Concept design options (compressor type, central vs local, treatment train, distribution strategy, resilience) |  | CIBSE, manufacturer |
| Outline compressed air strategy (pressure levels, air quality class, duty/standby, storage) |  | ISO 8573 air quality classes where relevant |
| Preliminary schematics and demand assessment |  | — |
| Outline specifications & preliminary cost plan |  | — |
| Design risk assessment (including pressure system hazards) |  | CDM, PSSR |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Coordinated design (compressor plant location, receiver siting, pipe routes, access, ventilation/cooling) |  | SHTM 00 |
| Spatial coordination with structure, electrical, ventilation and other services |  | SHTM 00 |
| Updated cost plan, risk register & high-level phasing / temporary supply strategy |  | — |
| Confirmation of critical user requirements |  | — |

Stage 4 – Technical Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full technical design drawings, schematics and pipework layouts |  | CIBSE, manufacturer |
| Detailed specifications (compressors, receivers, dryers, filters, pipework, valves, regulators, controls) |  | Relevant BS EN standards |
| Air treatment and quality specification (dryness, filtration, oil content) |  | ISO 8573 where applicable |
| Pressure system design and safety device schedule |  | PSSR |
| Control strategy, sequencing and BMS integration (if required) |  | — |
| Electrical design associated with compressors and controls |  | SHTM 06 series |
| Noise, ventilation and heat rejection design |  | — |
| Building Regulations / statutory compliance information |  | — |
| Pre-construction information & input to Construction Phase Plan |  | CDM |
| Designer’s Risk Assessment & residual risks |  | CDM, PSSR |
| Tender documentation / Scope of Works / pricing schedules |  | — |
| Competent Person review of design (where required under Written Scheme) |  | PSSR |

Stage 5 – Manufacturing and Construction

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Contractor method statements, detailed phasing & temporary compressed air arrangements |  | Where operationally required |
| Material & equipment certificates (compressors, receivers, dryers, filters, pipework, safety devices) |  | PED / BS EN standards |
| Installation of compressors, treatment plant, receivers, pipework and controls |  | — |
| Pressure testing, flushing and purity testing records |  | Relevant standards |
| Progress records, quality inspections, change control log |  | — |
| Temporary supply / hybrid working arrangements (if phased) |  | Where required |
| Decommissioning & strip-out records of redundant compressed air equipment |  | — |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full commissioning & validation records (pressure, flow, air quality, control sequences, safety devices) |  | Manufacturer, CIBSE |
| Safety valve setting and certification |  | PSSR |
| Air quality verification testing (particles, humidity, oil content as applicable) |  | ISO 8573 where relevant |
| Updated Written Scheme of Examination (if applicable) |  | PSSR |
| As-fitted drawings, schematics, valve schedules and pressure system documentation |  | PSSR |
| Comprehensive O&M manuals |  | SHTM 00 |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for estates and user staff |  | — |
| Residual risk register |  | CDM |
| Practical Completion / handover certificate |  | — |
| Formal client / Competent Person acceptance |  | PSSR where applicable |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Soft landings / post-occupancy review (performance, reliability, air quality, energy, user feedback) |  | SHTM 00 |
| Updated Written Scheme of Examination and inspection regime (if applicable) |  | PSSR |
| Ongoing maintenance, filter/dryer servicing and statutory examination programme |  | PSSR / manufacturer |
| Defects liability records & final account |  | — |
| Lessons learned report |  | SHTM 00 |

Cross-Stage / Continuous Deliverables

- Live Health & Safety File

- Project risk register (updated at each stage)

- Change control log

- Competent Person engagement at key gateways (where PSSR applies)

- Maintenance of adequate compressed air supply to critical users throughout the works (where required)

- Evidence of compliance with PSSR, PED, relevant BS EN standards, ISO 8573 (where applicable) and manufacturer requirements

- Full pressure testing, safety device certification and air quality records