Deliverables Checklist Replacement / Upgrade of Lifts (Vertical Transportation) in a Hospital Aligned to RIBA Plan of Work 2020 & relevant SHTMs

This checklist follows the same format as the previous medical gas, fire alarm, heating/ventilation and valve/boiler checklists. It is intended for projects involving the replacement, major modernisation or significant upgrade of lifts in hospital premises (passenger lifts, bed/passenger lifts, firefighting lifts, escape bed lifts, service lifts, etc.).

Primary SHTM / guidance references

| System Element | Key Guidance |
| --- | --- |
| Lifts (Vertical Transportation) | SHTM 08-02 – Specialist services: Lifts (V2, July 2015) |
| Supporting | SHTM 00 (Policies and principles) SFPN 3 – Escape bed lifts SHTM 81 / Firecode (firefighting & escape lifts) SHTM 06 series (electrical supplies) |
| Core Standards | BS EN 81 series (Safety rules for the construction and installation of lifts) BS 5655-6 (Selection and installation of new lifts) Lift Regulations / Lifts Directive CDM 2015 |

Key principles

- Hospitals rely on lifts for patients (including beds/trolleys), staff, visitors, equipment and goods.

- At least one bed/passenger lift should normally be available on the emergency electrical supply.

- Firefighting lifts and escape bed lifts have additional specific requirements.

- Continuity of vertical transportation must be maintained during the works wherever practicable (phased working or temporary measures).

- All work is subject to strict statutory safety regulations.

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Business case / need identification (lift age, reliability, capacity, accessibility, compliance) |  | SHTM 00, SHTM 08-02 |
| Strategic brief & project outcomes (service continuity, patient movement, fire strategy, accessibility) |  | SHTM 00 |
| High-level clinical / operational impact assessment |  | SHTM 00 |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Project Brief (scope: passenger, bed/passenger, firefighting, escape bed lifts etc.) |  | SHTM 00, SHTM 08-02 |
| Existing lift condition surveys (traffic analysis, performance, safety gear, controllers, doors) |  | SHTM 08-02 |
| Baseline traffic / usage data and residual life assessment |  | SHTM 08-02 |
| Initial risk register (service continuity, patient movement, fire strategy, structural) |  | SHTM 00, CDM |
| Project Execution Plan & procurement strategy |  | — |
| Engagement with Fire Safety Advisor (for firefighting / escape lifts) |  | SHTM 81, SFPN 3 |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Concept design options (full replacement vs modernisation, drive type, car sizes) |  | SHTM 08-02 |
| Outline lift strategy (number, type, capacity, speed, grouping, fire/escape designation) |  | SHTM 08-02 |
| Preliminary car sizes and door configurations (bed/passenger requirements) |  | SHTM 08-02 |
| Outline specifications & preliminary cost plan |  | — |
| Design risk assessment |  | CDM, SHTM 00, SHTM 08-02 |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Coordinated design (shafts, machine rooms / MRL, landings, structural supports, overrun) |  | SHTM 08-02 |
| Spatial coordination with structure, electrical, fire compartments and other services |  | SHTM 00 |
| Updated cost plan, risk register & high-level phasing / temporary cover strategy |  | — |
| Confirmation of firefighting / escape bed lift provisions |  | SHTM 81, SFPN 3 |

Stage 4 – Technical Design

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Full technical design drawings & schematics (shafts, cars, landings, machine rooms, interfaces) |  | SHTM 08-02 |
| Detailed specifications (drive system, controller, doors, safety gear, finishes, communication systems) |  | SHTM 08-02, BS EN 81 series |
| Structural design information (loads, fixings, machine room / pit) |  | — |
| Electrical design (main supply, emergency supply, lighting, alarms) |  | SHTM 06 series, SHTM 08-02 |
| Firefighting lift / escape bed lift specific requirements (controls, communications, power) |  | SHTM 81, SFPN 3, BS EN 81-72 |
| Building Regulations / statutory compliance information (including accessibility) |  | — |
| Pre-construction information & input to Construction Phase Plan |  | CDM |
| Designer’s Risk Assessment & residual risks |  | CDM, SHTM 08-02 |
| Tender documentation / Scope of Works / pricing schedules |  | — |
| Stakeholder / Fire Safety Advisor review and approval of design |  | SHTM 08-02 |

Stage 5 – Manufacturing and Construction

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Contractor method statements, detailed phasing & temporary vertical transportation arrangements |  | SHTM 08-02 |
| Material & equipment certificates (drive, controller, safety components, doors, car) |  | BS EN 81 series |
| Shaft preparation, structural works, machine room / MRL installation |  | — |
| Installation of lift equipment (car, counterweight, ropes/jack, doors, controller) |  | SHTM 08-02 |
| Electrical installation, emergency supply connections and testing |  | SHTM 06 series |
| Safety gear, governor, buffer and overspeed testing records |  | BS EN 81 series |
| Progress records, quality inspections, change control log |  | — |
| Temporary cover / hybrid working arrangements (if phased) |  | — |
| Decommissioning & strip-out records of redundant lift equipment |  | — |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Full commissioning, testing and validation records in accordance with SHTM 08-02 and BS EN 81 |  | SHTM 08-02 |
| Load testing, speed, levelling accuracy, door operation and safety device tests |  | BS EN 81 series |
| Firefighting / escape lift specific function tests (if applicable) |  | SHTM 81, SFPN 3 |
| As-fitted drawings, wiring diagrams and device schedules |  | SHTM 08-02 |
| Comprehensive O&M manuals, log book and rescue procedures |  | SHTM 08-02 |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for estates staff and rescue teams |  | SHTM 08-02 |
| Residual risk register |  | CDM |
| Practical Completion / handover certificate and statutory thorough examination |  | — |
| Formal acceptance by client / Responsible Person |  | SHTM 08-02 |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Soft landings / post-occupancy review (performance, reliability, user feedback) |  | SHTM 00 |
| Updated maintenance regime and planned preventive maintenance schedule |  | SHTM 08-02 |
| Ongoing thorough examination and inspection records (LOLER) |  | Statutory |
| Defects liability records & final account |  | — |
| Lessons learned report |  | SHTM 00 |

Cross-Stage / Continuous Deliverables

- Live Health & Safety File

- Project risk register (updated at each stage)

- Change control log

- Engagement with Fire Safety Advisor for firefighting / escape bed lifts

- Evidence of compliance with manufacturer instructions and BS EN 81 certification

- Maintenance of adequate vertical transportation capacity throughout the works

- LOLER thorough examination arrangements