Deliverables Checklist Replacement / Upgrade of Security Systems in a Hospital Aligned to RIBA Plan of Work 2020 & relevant Standards

This checklist follows the exact same format as the Electrical Services, Domestic Hot & Cold Water, Chilled Water, Steam, Fire Suppression, Medical Gas, Lifts and BMS checklists. It is intended for projects involving the replacement, major upgrade or significant modification of Security Systems in hospital premises (CCTV, Access Control, Intruder Detection, Staff Attack / Panic systems, control room equipment, and associated networks).

Primary Guidance References

| System Element | Key Guidance |
| --- | --- |
| Security Systems | NHS Scotland Security Standards / Guidance SHTM 00 – Policies and principles |
| Supporting | BS EN standards for CCTV, Access Control and Intruder Alarm systems Cybersecurity guidance (NHS and national standards) GDPR / UK Data Protection Act / Information Governance requirements CDM 2015 |
| Linked Systems | SHTM 06 series (Electrical power & networks) BMS / fire alarm interfaces (where applicable) Nurse Call / Staff Attack overlap |

Key Principles

- Security systems support the safety of patients, staff and visitors and the protection of assets.

- Continuity of security coverage must be maintained during the works.

- Cybersecurity, data protection and privacy (especially CCTV) are critical considerations.

- Systems must be designed with resilience, audit trails and appropriate access rights.

- Stakeholder engagement with Security, Estates, IT/Cyber, Information Governance and clinical teams is essential.

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Business case / need identification (system age, coverage gaps, reliability, compliance, risk profile) |  | SHTM 00 |
| Strategic brief & project outcomes (staff/patient safety, asset protection, situational awareness, compliance) |  | SHTM 00 |
| High-level security risk and operational impact assessment |  | NHS Scotland Security Standards |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Project Brief (scope: CCTV, access control, intruder, staff attack, control room) |  | SHTM 00 |
| Existing system condition surveys (cameras, readers, panels, recording, networks, coverage) |  | — |
| Security risk assessment review and gap analysis |  | NHS Scotland Security Standards |
| Initial risk register (loss of coverage, data protection, cybersecurity, operational impact) |  | SHTM 00, CDM |
| Project Execution Plan & procurement strategy |  | — |
| Engagement with Security, IT/Cyber, Information Governance, Estates and clinical stakeholders |  | Critical |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Concept design options (camera technology, access control architecture, integration, cloud vs on-premise) |  | BS EN standards |
| Outline security strategy (coverage, detection, response, recording, retention) |  | NHS Scotland Security Standards |
| Preliminary layouts (camera locations, access points, control room) |  | — |
| Outline specifications & preliminary cost plan |  | — |
| Design risk assessment (including privacy and cybersecurity) |  | CDM, GDPR |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Coordinated design (camera positions, reader locations, cabling routes, control room, equipment rooms) |  | — |
| Spatial coordination with structure, ceilings, lighting, other services and fire compartments |  | SHTM 00 |
| Updated cost plan, risk register & high-level phasing / temporary coverage strategy |  | — |
| Confirmation of network and power resilience requirements |  | SHTM 06 linked |

Stage 4 – Technical Design

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full technical design drawings, schematics, camera schedules and access control schedules |  | BS EN standards |
| Detailed specifications (cameras, recorders/VMS, readers, controllers, detectors, software, networks) |  | Manufacturer + BS EN |
| Network architecture, cybersecurity design and hardening measures |  | NHS Cyber standards |
| Data protection / privacy impact assessment (DPIA) for CCTV and access control |  | GDPR / UK DPA |
| Recording, retention, export and audit trail design |  | Information Governance |
| Electrical design associated with power and backup |  | SHTM 06 series |
| Interface design with other systems (fire, BMS, nurse call, lifts if required) |  | — |
| Building Regulations / statutory compliance information |  | — |
| Pre-construction information & input to Construction Phase Plan |  | CDM |
| Designer’s Risk Assessment & residual risks |  | CDM |
| Tender documentation / Scope of Works / pricing schedules |  | — |
| Stakeholder review and approval of design (Security, IG, Cyber, Estates) |  | Essential |

Stage 5 – Manufacturing and Construction

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Contractor method statements, detailed phasing & temporary security coverage arrangements |  | Critical |
| Material & equipment certificates (cameras, recorders, readers, controllers, software licences) |  | Manufacturer |
| Installation of cameras, readers, detectors, cabling, control equipment and networks |  | — |
| Network configuration, cybersecurity hardening and testing records |  | Cyber standards |
| Progress records, quality inspections, change control log |  | — |
| Temporary coverage / hybrid working arrangements (if phased) |  | Essential |
| Decommissioning & secure destruction records of redundant equipment and data |  | GDPR / IG |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Full commissioning, functional testing and performance verification records |  | BS EN / manufacturer |
| Camera coverage, image quality and recording verification |  | — |
| Access control, anti-passback, audit trail and integration testing |  | — |
| Cybersecurity testing and vulnerability confirmation |  | NHS Cyber standards |
| As-fitted drawings, camera schedules, access schedules, network diagrams and configuration backups |  | — |
| Comprehensive O&M manuals, user guides and administrator documentation |  | SHTM 00 |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for Security, Estates and Control Room staff |  | — |
| Residual risk register |  | CDM |
| Practical Completion / handover certificate |  | — |
| Formal acceptance by Security, Information Governance and client |  | Essential |
| Updated DPIA and data retention policies |  | GDPR / IG |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant Notes |
| --- | --- | --- |
| Soft landings / post-occupancy review (coverage effectiveness, usability, false alarms, user feedback) |  | SHTM 00 |
| Updated operational procedures, monitoring protocols and incident response |  | NHS Scotland Security Standards |
| Ongoing maintenance, software update, cybersecurity and data management regime |  | — |
| Defects liability records & final account |  | — |
| Lessons learned report |  | SHTM 00 |

Cross-Stage / Continuous Deliverables

- Live Health & Safety File

- Project risk register (updated at each stage)

- Change control log

- Security, IT/Cyber and Information Governance engagement at key gateways

- Maintenance of continuous security coverage throughout the works

- Evidence of compliance with NHS Scotland Security Standards, BS EN standards, cybersecurity requirements and GDPR

- Secure data handling and destruction records