## Risk Register
ACTIVE RISK REGISTER — Ward 3 Mental Health Unit Reduced Ligature Refurbishment
Project: Stage 3 Refurbishment ¦ Client: Serco / NHS ¦ Updated: 07 May 2026 ¦ v2.0 — Patient Risk Assessment integrated ¦ Review Frequency: Weekly
Risk ID | Element / Activity | Hazard / Risk | Persons at Risk | Inherent Likelihood | Inherent Impact | Inherent Risk | Controls | Residual Risk | Accountability | Risk Owner | Status | Date Raised | Last Review Date | Next Review Date | Actions Required | Action Due Date | Progress Notes
R-01 | General Site Presence in Live MHU | Patients accessing tools, materials or unsecured areas | Patients, Staff | High | High | HIGH | All rooms locked when contractors not inside; daily tool checklist & sign-out; no tools left unattended; clinical induction on patient behaviours; Pinpoint staff attack alarm issued to every contractor. | Low | Nurse in Charge (NHS) / MPMH Supervisor |  | OPEN | 05/04/2026 |  |  |  |  | Accountability updated to NHS primary per patient risk assessment review (Apr 2026)
R-02 | General Site Presence in Live MHU | Noise disturbing patients (power tools, hammering) | Patients, Staff | Med | High | MEDIUM | Battery tools preferred; work only during agreed hours; noise monitoring (≤80 dB); toolbox talks on minimising noise; clinical team briefed on schedule. | Low | MPMH - Lee Gemmel |  | OPEN | 05/04/2026
R-03 | Door Replacement | Unlocked door during replacement allowing patient access to tools | Patients | High | High | HIGH | One door replaced per day; room locked immediately after new door fitted; tools removed/secured before leaving room; clinical induction + daily checklist. | Low | MPMH - Lee Gemmel |  | OPEN | 05/04/2026
R-04 | Door Replacement | New door monitors (KG500) creating unintended ligature points if not sealed | Patients | Med | High | MEDIUM | KG500 fitted and tested as part of Kingsway complete system; anti-pick sealant applied; Warringtonfire FoA compliance confirmed. | Low | MPMH + Principal Designer |  | OPEN | 05/04/2026
R-05 | Window Replacement | Open window opening allowing escape or ligature attempt | Patients | High | High | HIGH | Windows removed and sealed externally; temporary anti-ligature blanking panel fitted immediately; no internal reveal work required after external sealing; ceiling void wiring done from loft (no room entry needed). | Low | Polar + MPMH (Lee Gemell and A. sanson) |  | OPEN | 05/04/2026
R-06 | Window Replacement | Contractors leaving window unsecured while working | Patients | High | High | HIGH | External sealing protocol strictly followed; daily checklist confirms opening secured; no work left overnight with open aperture. | Low | Polar Supervisor |  | OPEN | 05/04/2026
R-07 | Ensuite & Room Refurbishment (Strip-out) | Dust from vinyl removal and IPS panel removal contaminating air | Patients, Staff | High | High | HIGH | HAI-SCRIBE controls (Class II/III); on-tool extraction + FFP3 masks; water suppression instead of dry sweeping; daily deep clean of work area. | Low | MPMH - Lee Gemmel |  | OPEN | 05/04/2026
R-08 | Ensuite & Room Refurbishment (Strip-out) | Manual handling of heavy debris (old flooring, IPS panels) | Contractors | High | Med | MEDIUM | Mechanical aids and team lifting; manual handling toolbox talk; reduce load sizes. | Low | MPMH - Lee Gemmel |  | OPEN | 05/04/2026
R-09 | Ensuite & Room Refurbishment (Fit-out) | Altro Whiterock cladding and Altro Aquarius flooring creating slip/trip hazards during installation | Patients, Staff, Contractors | Med | Med | LOW | Housekeeping maintained; non-slip flooring installed progressively; barriers and signage around wet works. | Low | MPMH - Lee Gemmel |  | OPEN | 05/04/2026
R-10 | Tool Control & Materials | Tools or materials left in room creating ligature or weapon risk | Patients | High | High | HIGH | Daily tool checklist (sign in/out); tools removed at end of every shift; secure tool bags/lockable chests; no overnight storage in rooms. | Low | Nurse in Charge (NHS) / All Contractors |  | OPEN | 05/04/2026 |  |  |  |  | Accountability updated to NHS primary per patient risk assessment review (Apr 2026)
R-11 | Working at Height | Falls from steps or hop-ups during cladding/IPS installation | Contractors | Med | High | MEDIUM | Stepladder permit required daily; PASMA-trained operatives; no work below others. | Low | MPMH |  | OPEN | 05/04/2026
R-12 | Live Services / Electrical | Electric shock or gas leak during service isolation | Contractors | High | High | HIGH | Services isolated by authorised persons (Robert Smith / Stephen Donovan); confirmation drawings used; lock-out/tag-out procedures. | Low | Serco Electrical AP |  | OPEN | 05/04/2026
R-13 | Waste Management | Waste left in room or corridor creating trip or ligature hazard | Patients, Staff | Med | High | MEDIUM | Lockable/lidded skips used; waste removed daily; no accumulation allowed. | Low | MPMH - Lee Gemmel |  | OPEN | 05/04/2026
R-14 | Patient Behaviour / Security | Patient attempts to enter work area or shows distress | Patients, Staff, Contractors | High | High | HIGH | Stop work immediately; secure area and alert nursing staff; never manage patient behaviour yourself. | Low | Nurse in Charge (NHS) / Ward Team |  | OPEN | 05/04/2026 |  |  |  |  | Accountability updated to NHS primary per patient risk assessment review (Apr 2026)
R-15 | Overall Project | Cumulative disruption to patients over project duration | Patients, Staff | Med | High | MEDIUM | Maximum 3 rooms worked at a time; weekly ward briefings; clear communication of schedule to ward team. | Low | NHS Ward Manager / Serco PM |  | OPEN | 05/04/2026 |  |  |  |  | Accountability updated to NHS primary per patient risk assessment review (Apr 2026)
PATIENT-SPECIFIC RISKS — Mental Health Assessment (NHS Accountability)
R-16 | Emergency Response — Pinpoint Alarm | Lack of contractor understanding of when/how to activate Pinpoint alarm | Patients, Contractors | High | High | HIGH | Pinpoint alarm use covered in induction and reviewed as required throughout works; alarm functionality verified before works commence each day. | Low | Nurse in Charge (NHS) |  | OPEN | 05/04/2026 |  |  | Confirm NHS lead named; verify induction covers MH-01 controls |  | Source: MH Patient Risk Assessment v2.0 — MH-01
R-17 | External Fire Doors Left Open | Contractor propping fire doors for access/ventilation — patient absconding or safeguarding breach to FVRH grounds | Patients | High | High | HIGH | Fire doors never propped; alarms active; staffed access only; time-limited openings agreed with Nurse in Charge only. | Low | Nurse in Charge (NHS) / Contractor |  | OPEN | 05/04/2026 |  |  | Confirm NHS lead named; verify induction covers MH-05 controls |  | Source: MH Patient Risk Assessment v2.0 — MH-05
R-18 | Hazardous Substances (COSHH) — Patient Exposure | Unsafe storage/use of adhesives, solvents; vapours causing agitation or misperception in patients with neuropsychiatric conditions; biological hazard (blood/bodily fluids) | Patients, Staff, Contractors | High | High | HIGH | Locked COSHH storage; minimal quantities on-site; no unlabelled containers; applied only when patients absent from area; immediate removal after task; good ventilation maintained; IPC Nurse notified if exposure suspected. | Low | IPC Nurse (NHS) / Nurse in Charge / Contractor |  | OPEN | 05/04/2026 |  |  | Confirm NHS lead named; verify induction covers MH-06 controls |  | Source: MH Patient Risk Assessment v2.0 — MH-06
R-19 | Multiple Contractors Simultaneously on Ward | Noise, congestion, unfamiliar interactions causing patient anxiety, agitation or behavioural escalation | Patients, Staff | High | High | HIGH | Phased works; mental health induction for all contractors; no unsupervised patient interaction; noisy works scheduled for agreed windows; stop-work authority given if distress observed; Nurse in Charge intervenes immediately. | Low | Nurse in Charge (NHS) / Serco PM |  | OPEN | 05/04/2026 |  |  | Confirm NHS lead named; verify induction covers MH-07 controls |  | Source: MH Patient Risk Assessment v2.0 — MH-07
R-20 | Contractor Movement in Incorrect Areas | Contractors straying into unauthorised ward areas — unwanted patient interaction causing fright, verbal/physical incident | Patients, Staff, Contractors | Medium | High | MEDIUM | Ward layout covered in induction; all contractors issued Pinpoint alarms; escorted access to new areas; immediate work pause if incident occurs. | Low | Nurse in Charge (NHS) |  | OPEN | 05/04/2026 |  |  | Confirm NHS lead named; verify induction covers MH-08 controls |  | Source: MH Patient Risk Assessment v2.0 — MH-08
R-21 | Poor Communication — Contractors & Clinical Staff | Insufficient shared awareness of risks; tools/equipment left in corridors; clinical staff unable to react to hazards in time | Patients, Staff | High | High | HIGH | Joint daily briefings between clinical and Serco staff; weekly progress reviews; regular joint walk-round inspections; immediate escalation channel agreed; any communication failure triggers urgent review. | Low | NHS Health Staff / Serco PM / Contractor |  | OPEN | 05/04/2026 |  |  | Confirm NHS lead named; verify induction covers MH-09 controls |  | Source: MH Patient Risk Assessment v2.0 — MH-09
R-22 | Access Equipment — Patient Use (Roof Access) | Patient accessing ladders or other access equipment left unattended — potential for fall/serious injury from roof access | Patients | High | High | HIGH | All access equipment stored correctly; never left unattended; removed and secured immediately after use; Nurse in Charge initiates response immediately if breach detected. | Low | Nurse in Charge (NHS) / Serco PM / Contractor |  | OPEN | 05/04/2026 |  |  | Confirm NHS lead named; verify induction covers MH-10 controls |  | Source: MH Patient Risk Assessment v2.0 — MH-10
R-23 | Patient & Staff Confidentiality | Contractors overhearing confidential information; mobile devices inadvertently capturing images of patients or staff, or docuemnts left in room | Patients, Staff | High | Medium | MEDIUM | Confidentiality obligations covered during induction; no photography or recording permitted on ward; immediate escalation to Nurse in Charge if breach suspected. | Low | Nurse in Charge (NHS) / Serco PM / Contractor |  | OPEN | 05/04/2026 |  |  | Confirm NHS lead named; verify induction covers MH-13 controls |  | Source: MH Patient Risk Assessment v2.0 — MH-13
R-24 | Food & Drink Left Unattended by Contractors | Unsecured contractor food/drink consumed by patients who may have diet or fluid restrictions | Patients | Medium | High | MEDIUM | No food/drink held in unsecured patient areas; covered in induction; immediate removal if found; escalated to Nurse in Charge. | Low | Nurse in Charge (NHS) / Serco PM / Contractor |  | OPEN | 05/04/2026 |  |  | Confirm NHS lead named; verify induction covers MH-14 controls |  | Source: MH Patient Risk Assessment v2.0 — MH-14
RISK MATRIX LEGEND |  |  |  | STATUS GUIDE
HIGH |  |  |  | OPEN |  | Risk identified; controls in place but being monitored
MEDIUM |  |  |  | IN PROGRESS |  | Mitigation actions underway
LOW |  |  |  | MONITORING |  | Residual risk acceptable; under routine review
|  |  |  | ESCALATED |  | Risk elevated — senior management intervention required
|  |  |  | CLOSED |  | Risk no longer active