Deliverables Checklist Replacement / Upgrade of Steam Systems in a Hospital Aligned to RIBA Plan of Work 2020 & relevant SHTMs / Standards

This checklist follows the exact same format as the Electrical Services, Domestic Hot & Cold Water, Chilled Water, Medical Gas, Lifts and BMS checklists. It is intended for projects involving the replacement, major upgrade or significant modification of Steam Systems in hospital premises (steam generation, distribution, condensate recovery, pressure reducing stations, humidification, sterilisation supplies, and associated controls).

Primary SHTM / Guidance References

| System Element | Key Guidance |
| --- | --- |
| Steam Systems | SHTM 00 – Policies and principles Pressure Systems Safety Regulations (PSSR) 2000 HSE Approved Code of Practice and guidance on PSSR |
| Supporting | SHTM 06 series (Electrical power) CIBSE Guides Manufacturer standards Legacy references to older SHTM boiler/steam guidance where still applicable |
| Core Standards | BS EN 12953 / BS EN 12952 (boilers), BS 1113 / equivalent, INDG261, CDM 2015, BESSafe or equivalent water treatment guidance |

Key Principles

- Steam systems are pressure systems and fall under the Pressure Systems Safety Regulations (PSSR).

- A Written Scheme of Examination is mandatory.

- Continuity of steam supply to critical users (sterile services, humidification, kitchens, process loads) must be maintained where clinically or operationally required.

- Water treatment, condensate management, and safety device integrity are critical.

- Competent Person involvement is required for design examination, certification and ongoing inspections.

Stage 0 – Strategic Definition

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Business case / need identification (system age, reliability, safety, energy efficiency, residual life) |  | SHTM 00, PSSR |
| Strategic brief & project outcomes (safety, continuity of supply, compliance, energy performance) |  | SHTM 00 |
| High-level clinical / operational impact assessment |  | SHTM 00 |

Stage 1 – Preparation and Briefing

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Project Brief (scope of steam generation, distribution, condensate and user modifications) |  | SHTM 00 |
| Existing system condition surveys (boilers, distribution, PRVs, traps, condensate, water treatment) |  | PSSR |
| Review of existing Written Scheme of Examination and inspection history |  | PSSR |
| Initial risk register (pressure system failure, loss of steam, burns, water treatment) |  | SHTM 00, CDM, PSSR |
| Project Execution Plan & procurement strategy |  | — |
| Engagement with Competent Person, estates and clinical stakeholders |  | PSSR |

Stage 2 – Concept Design

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Concept design options (boiler type, pressure levels, distribution strategy, condensate recovery, resilience) |  | CIBSE, manufacturer |
| Outline steam system strategy (generation, distribution, reduction, condensate) |  | — |
| Preliminary schematics and load assessment |  | — |
| Outline specifications & preliminary cost plan |  | — |
| Design risk assessment (including pressure system hazards) |  | CDM, PSSR |

Stage 3 – Spatial Coordination

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Coordinated design (boiler plant, pipe routes, PRV stations, condensate receiver locations, access) |  | SHTM 00 |
| Spatial coordination with structure, electrical, ventilation and other services |  | SHTM 00 |
| Updated cost plan, risk register & high-level phasing / temporary steam strategy |  | — |
| Confirmation of critical user resilience requirements |  | — |

Stage 4 – Technical Design

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Full technical design drawings, schematics and pipework layouts |  | CIBSE, manufacturer |
| Detailed specifications (boilers, burners, pipework, valves, PRVs, traps, insulation, controls, water treatment) |  | Relevant BS EN standards |
| Pressure system design and safety device schedule |  | PSSR |
| Water treatment / chemical dosing / blowdown strategy |  | Manufacturer / BESSafe principles |
| Control strategy, sequences and BMS integration |  | — |
| Electrical design associated with boilers, pumps and controls |  | SHTM 06 series |
| Building Regulations / statutory compliance information |  | — |
| Pre-construction information & input to Construction Phase Plan |  | CDM |
| Designer’s Risk Assessment & residual risks |  | CDM, PSSR |
| Tender documentation / Scope of Works / pricing schedules |  | — |
| Competent Person review of design (where required under Written Scheme) |  | PSSR |
| DSEAR risk assessment for boiler fuel supply and combustion |  | DSEAR |

Stage 5 – Manufacturing and Construction

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Contractor method statements, detailed phasing & temporary steam arrangements |  | Critical for process users |
| Material & equipment certificates (boilers, pipework, valves, safety devices) |  | PED / BS EN standards |
| Installation of boilers, pipework, PRVs, traps, insulation and controls |  | — |
| NDT, pressure testing and welding records |  | PSSR / BS standards |
| Water treatment system installation and initial dosing records |  | — |
| Progress records, quality inspections, change control log |  | — |
| Temporary steam / hybrid working arrangements (if phased) |  | Essential where required |
| Decommissioning & strip-out records of redundant steam equipment |  | — |

Stage 6 – Handover

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Full commissioning & validation records (pressure, temperature, safety device function, control sequences) |  | Manufacturer, CIBSE |
| Safety valve setting and certification |  | PSSR |
| Performance testing of boilers and distribution |  | — |
| Updated Written Scheme of Examination |  | PSSR |
| As-fitted drawings, schematics, valve schedules and pressure system documentation |  | PSSR |
| Comprehensive O&M manuals |  | SHTM 00 |
| Updated Health & Safety File |  | CDM |
| Training & demonstration records for estates staff |  | SHTM 00 |
| Residual risk register |  | CDM |
| Practical Completion / handover certificate |  | — |
| Formal client / Competent Person acceptance |  | PSSR |

Stage 7 – Use

| Deliverable | Status / Evidence | Relevant SHTM / Notes |
| --- | --- | --- |
| Soft landings / post-occupancy review (performance, reliability, safety, energy) |  | SHTM 00 |
| Updated Written Scheme of Examination and inspection regime |  | PSSR |
| Ongoing water treatment, maintenance and statutory examination programme |  | PSSR |
| Defects liability records & final account |  | — |
| Lessons learned report |  | SHTM 00 |

Cross-Stage / Continuous Deliverables

- Live Health & Safety File

- Project risk register (updated at each stage)

- Change control log

- Competent Person engagement at key gateways

- Maintenance of continuous steam supply to critical users throughout the works (where required)

- Evidence of compliance with PSSR, PED, relevant BS EN standards and manufacturer requirements

- Full pressure testing, NDT and safety device certification records

- Evidence of current PVG Scheme membership for all contractor personnel attending site

- Where works are in, adjacent to, above or below a room housing ionising-radiation imaging equipment (CT, X-ray, fluoroscopy, nuclear medicine): confirm Radiation Protection Adviser (RPA) sign-off on shielding integrity per the Room/Ward/Theatre Refresh checklist - a separate gate from HAI-SCRIBE, not covered by it